## 08-14-20
Department: |  | Department of Environmental Quality
Report Date: |  | 8/14/20
CAPITAL IMPROVEMENT PROJECTS REPORT | [9 empty] | CAPITAL IMPROVEMENT PROJECTS REPORT
Project Identification | [5 empty] | Current Construction Phase |  |  |  | Funding and Sources |  |  | Adequacy of Funding |  |  | Comments
# | Budget Code | Fund Code | SCO Project ID# | Project Title | R&R Project? (Y/N) | Land Acquisition | Design Stages (Pick one from dropdown) | Construction Stage (Pick % complete from dropdown) | Projected Completion Date from Current Project Phase (Enter mo.&yr: XX/20XX) | Amt Expended Project to Date | Primary Funding Source (Pick one from dropdown) | Secondary Funding Source (Pick one from dropdown) | Is the project adequately funded? (Y/N) | How do current cost estimates compare to the project's initial authorized budget? | Will scope reductions be necessary to complete the project within its initial authorized budget? (Y/N) | Notes/Comments
1 | 40374 | 4X15 |  | DWR - Reedy Creek Renovations | Yes |  |  | Complete | Complete/Final Billing | 150026 | Debt Financed |  | Yes | On budget | No | Project Balance of $29,773.87
7 | 41316 | 4P30 | 13-10449-01A | ADM - R & R Innovation Center Building SEC | Yes | - | - | 76%-100% |  | 304612 | General Fund | Receipts | Yes | On budget | No | Project Balance $20,376.26
12 | 41516 | 4T16 |  | DWR - Planning SL 2010-143 | No | - | - | - |  | 27223.75 | General Fund |  | Yes | On budget | No | Project Balance $47,776.25 - Hydrologic modeling is occurring and DWR will exhaust funds by December 2020.
13 | 41516 | 4T17 |  | DWR - State Local Projects | No | - | - | - |  | 1206734.28 | General Fund | Receipts | Yes | On budget | No | Project Balance $187,438.98
15 | 41616 | 4U07 |  | DWR - State Local Projects | No | - | - | - |  | 938929 | General Fund | Receipts | Yes | On budget | No | Project Balance $396,191.02
16 | 41616 | 4U08 |  | DWR - Cape Fear Lock & Dam #2 | No | - | - | - |  | 29315.92 | General Fund |  | Yes | On budget | No | Project Balance $470,684.08
17 | 41616 | 4U10 |  | DWR - EQIP | No | - | - | - |  | 1610765 | General Fund | Receipts | Yes | On budget | No | Project Balance $389,235.40
18 | 41616 | 4U11 |  | DWR - Town of Burgaw - Pender | No | - | - | - |  | 347000 | General Fund |  | Yes | On budget | No | Project Balance $0.00 - TO DROP OFF NEXT REPORT
20 | 41616 | 4U20 |  | DMF - HVAC Controls System Upgrade | Yes | - |  | 76%-100% | Complete/Final Billing | 411461.61 | General Fund |  | Yes | On budget | No | Project Balance $21,934.41
21 | 41616 | 4U21 |  | DWR - Roof Replacement Reed Creek | Yes | - | Schematic Design (SD) | Complete | Complete/Final Billing | 215918 | General Fund | Receipts | Yes | On budget | No | Project Balance $7,876.70
22 | 41716 | 4V11 |  | DWR - EQUIP | No | - | - | - |  | 1927255 | General Fund |  | Yes | On budget | No | Project Balance $72,744.64
23 | 41716 | 4V12 |  | DWR - State Local Projects | No | - | - | - |  | 2422040.29 | General Fund | Receipts | Yes | On budget | No | Project Balance $546,895.71
25 | 41716 | 4V21 |  | DWR - Roof Replacement Reed Creek | Yes | - | Schematic Design (SD) | 76%-100% | SCO- Spring 2021 | 0 | General Fund |  | Yes | On budget | No | Project Balance $567,100
26 | 41716 | 4V23 |  | DMF - Roof Maintenance Building | Yes | - |  | Complete | Complete/Final Billing | 384768 | General Fund |  | Yes | On budget | No | Project Balance $101,872.33
27 | 41716 | 4V24 |  | DMF - Dock Structural Repairs | Yes | - | Schematic Design (SD) | - | SCO- Summer 2021 | 92803 | General Fund |  | Yes | On budget | No | Project Balance $ 588,214.06
28 | 41816 | 4Y01 |  | DWR - Princeville Flood | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,400,000 - DWR will be signing a Project Partnership Agreement with USACE by October 2020 and funds will be expended by October 2021.
29 | 41816 | 4Y02 |  | DWR - Carolina Beach CSDR | No | - | - | - |  | 930531.84 | General Fund | Receipts | Yes | On budget | No | Project Balance $906,354.11
30 | 41816 | 4Y03 |  | DWR - Kure Beach | No | - | - | - |  | 1423871.33 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,031,854.37
31 | 41816 | 4Y04 |  | DWR - Planning Assistance to Communities | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $244,613.13
32 | 41816 | 4Y05 |  | DWR - Bogue Banks CSRM | No | - | - | - |  | 173486.92 | General Fund | Receipts | Yes | On budget | No | Project Balance $28,513.08
33 | 41816 | 4Y06 |  | DWR - Wilmington Harbor DA Maintenance | No | - | - | - |  | 7022549.85 | General Fund | Receipts | Yes | On budget | No | Project Balance $735.00
34 | 41816 | 4Y07 |  | DWR - Surf City N Topsail CSRM | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $255,000
35 | 41816 | 4Y08 |  | DWR - West Onslow Beach CSRM | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $220,500
36 | 41816 | 4Y09 |  | DWR - Neuse River - Goldsboro | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $333,500
37 | 41816 | 4Y10 |  | DWR - Concord Stream Ecosystem Rest | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,023,000
39 | 41816 | 4Y12 |  | DWR - Lumberston Flood Damage Red | No | - | - | - |  | 0 | General Fund |  | Yes | On budget | No | Project Balance $125,000
40 | 41816 | 4Y13 |  | DWR - EQUIP | No | - | - | - |  | 729135 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,293,946.48
41 | 41816 | 4Y14 |  | DWR - Everett e Jordan | No | - | - | - |  | 209207.53 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,816,465.63
42 | 41816 | 4Y16 |  | DWR - State Local Projects | No | - | - | - |  | 468402 | General Fund | Receipts | Yes | On budget | No | Project Balance $2,437,586.93
43 | 41816 | 4Y17 |  | DWR - Brunswick Ft Anderson | No | - | - | - |  | 0 | General Fund |  | Yes | On budget | No | Project Balance $487,000
44 | 41816 | 4Y18 |  | DWR - North Topsail Shoreline | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $ 1,500,000
45 | 41816 | 4Y19 |  | DWR - Lindsey BR Dam Repair & Stream Res | No | - | - | - |  | 89250 | General Fund |  | Yes | On budget | No | Project Balance $1,910,750.00
46 | 41816 | 4Y20 |  | DWR - Morehead City Maintenance | No | - | - | - |  | 300000 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,872,000.00
48 | 41816 | 4Y23 |  | DWR - Wrightsville Beach CSDR | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $2,206,487
49 | 41816 | 4Y25 |  | DWR - Cape Fear Lock & Dam #2 #3 Fish Ramp | No |  |  |  |  | 0 | General Fund |  | Yes | On budget | No | Project Balance $ 840,000
50 | 41816 | 4Y26 |  | DWR - Town of Rutherfordton Stream Restoration | No |  |  |  |  | 0 | General Fund |  | Yes | On budget | No | Project Balance $500,000
51 | 41816 | 4Y27 |  | DWR - Ararat River Greenway | No |  |  |  |  | 0 | General Fund |  | Yes | On budget | No | Project Balance $ 500,000
52 | 41816 | 4Y28 |  | DWR - Ocean Isle CSDR | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,040,016.76
53 | 41816 | 4Y29 |  | DWR - Reedy Creek Complex | Yes | - | - | Schmatic Design | SCO- Spring 2021 | 103448.14 | General Fund |  | Yes | On budget | No | Project Balance $1,364,631.70
55 | 41816 | 4Y33 |  | DCM - Meter Point Tract | No |  |  | 76%-100% |  | 904614 | General Fund | Receipts | Yes | On budget | No | Project Balance $45.06
56 | 41816 | 4Y34 |  | DWR- Reedy Creek Renovations | Yes |  |  | 25%-50% | Ongong | 94610 | General Fund | Receipts | Yes | On budget | No | Projedct Balance $343,158.27
56 | 41916 | 4Z01 |  | DCM - Primland Tract | No |  |  |  |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $159,870.00, DCM still awaits final paperwork approval from acquisition partners @ US Air Force & The Nature Conservancy. The project remains on schedule.