## Admin
DENR |  | Department of Environmental Quality | [7 empty] | Department:
Report Date: |  | 01/01/21 | [7 empty] | Report Date:
CAPITAL IMPROVEMENT PROJECTS REPORT | [9 empty] | CAPITAL IMPROVEMENT PROJECTS REPORT
Project Identification | [5 empty] | Current Construction Phase |  |  |  | Funding and Sources |  |  | Adequacy of Funding |  |  | Comments
# | Budget Code | Fund Code | SCO Project ID# | Project Title | R&R Project? (Y/N) | Land Acquisition | Design Stages (Pick one from dropdown) | Construction Stage (Pick % complete from dropdown) | Projected Completion Date from Current Project Phase (Enter mo.&yr: XX/20XX) | Amt Expended YTD | Primary Funding Source (Pick one from dropdown) | Secondary Funding Source (Pick one from dropdown) | Is the project adequately funded? (Y/N) | How do current cost estimates compare to the project's initial authorized budget? | Will scope reductions be necessary to complete the project within its initial authorized budget? (Y/N) | Notes/Comments
1 | 40374 | 4X15 |  | DWR - Reedy Creek Renovations | Yes |  |  | Complete |  | 160785.63 | Debt Financed |  | Yes | On budget | No | Project Balance of $19,014.87
2 | 41316 | 4P30 | 13-10449-01A | ADM - R & R Innovation Center Building SEC | Yes |  |  | 76%-100% |  | 304612 | General Fund | Receipts | Yes | On budget | No | Project Balance $20,376.26
3 | 41516 | 4T17 |  | DWR - State Local Projects | No |  |  |  |  | 1206734.28 | General Fund | Receipts | Yes | On budget | No | Project Balance $187,438.98
4 | 41616 | 4U07 |  | DWR - State Local Projects | No |  |  |  |  | 1018119.9 | General Fund | Receipts | Yes | On budget | No | Project Balance $317,000.00
5 | 41616 | 4U08 |  | DWR - Cape Fear Lock & Dam #2 | No |  |  |  |  | 29315.92 | General Fund |  | Yes | On budget | No | Project Balance $470,684.08
6 | 41616 | 4U10 |  | DWR - EQIP | No |  |  |  |  | 1740267.02 | General Fund | Receipts | Yes | On budget | No | Project Balance $259,732.98
7 | 41616 | 4U20 |  | DMF - HVAC Controls System Upgrade | Yes |  | Final Drawings/Bid (FD) | Complete | Summer 2020 | 432910.8 | General Fund |  | Yes | On budget | No | Project Balance $485.22
8 | 41716 | 4V11 |  | DWR - EQUIP | No |  |  |  |  | 1946876.19 | General Fund |  | Yes | On budget | No | Project Balance $53,123.81
9 | 41716 | 4V12 |  | DWR - State Local Projects | No |  |  |  |  | 2497734.29 | General Fund | Receipts | Yes | On budget | No | Project Balance $471,201.71
10 | 41716 | 4V21 |  | DWR - Roof Replacement Reed Creek | Yes |  | Final Drawings/Bid (FD) | 76%-100% | 2021-01-01 | 25840 | General Fund |  | Yes | On budget | No | Project Balance $541,260.00
11 | 41716 | 4V23 |  | DMF - Roof Maintenance Building | Yes |  |  | Complete | Spring 2019 | 435356.3 | General Fund |  | Yes | On budget | No | PROJECT COMPLETE - TO BE OFF NEXT REPORT
12 | 41716 | 4V24 |  | DMF - Dock Structural Repairs | Yes |  | Final Drawings/Bid (FD) | 0-25% | Winter 2021 | 110092.8 | General Fund |  | Yes | On budget | No | Project Balance $ 622,207.76
13 | 41816 | 4Y13 |  | DWR - EQUIP | No |  |  |  | Ongoing | 1104431.33 | General Fund | Receipts | Yes | On budget | No | Project Balance $918,650.48
14 | 41816 | 4Y14 |  | DWR - Everett e Jordan | No |  |  |  | Ongoing | 2025673.16 | General Fund | Receipts | Yes | On budget | No | Project Balance $15,167.24
15 | 41816 | 4Y16 |  | DWR - State Local Projects | No |  |  |  | Ongoing | 974691.16 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,931,297.54
16 | 41816 | 4Y17 |  | DWR - Brunswick Ft Anderson | No |  |  | 51-75% | Spring 2021 | 0 | General Fund |  | Yes | On budget | No | Project Balance $487,000
17 | 41816 | 4Y19 |  | DWR - Lindsey BR Dam Repair & Stream Res | No |  |  | 0-25% | Spring 2021 | 1389250 | General Fund |  | Yes | On budget | No | Project Balance $610,750.00
18 | 41816 | 4Y26 |  | DWR - Town of Rutherfordton Stream Restoration | No |  |  | 0-25% | Spring 2021 | 0 | General Fund |  | Yes | On budget | No | Project Balance $500,000
19 | 41816 | 4Y27 |  | DWR - Ararat River Greenway | No |  |  | 0-25% | Spring 2021 | 0 | General Fund |  | Yes | On budget | No | Project Balance $ 500,000
20 | 41816 | 4Y29 |  | DWR - Reedy Creek Complex | Yes |  | Final Drawings/Bid (FD) | 25-50% | Winter 2021 | 111312.54 | General Fund |  | Yes | On budget | No | Project Balance $1,356,767.30
21 | 41816 | 4Y33 |  | DCM - Meter Point Tract | No |  |  | 76%-100% |  | 904614 | General Fund |  | Yes | On budget | No | Project Balance $45.06
22 | 41816 | 4Y34 |  | DWR- Reedy Creek Renovations | Yes |  | Final Drawings/Bid (FD) | 25-50% |  | 267484.89 | General Fund | Receipts | Yes | On budget | No | Projedct Balance $178,159.58
23 | 41916 | 4Z01 |  | DCM - Primland Tract | No |  |  |  |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $159,870.00; easement requirement being worked with Dept of Defense
24 | 42016 | 4O01 |  | DWR - Princeville Flood | No |  |  | 0-25% | Spring 2024 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $3,465,000.00
25 | 42016 | 4O02 |  | DWR - Carolina Beach CSDR | No |  |  | 0-25% | Next cycle - Spring 2021 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,750,000.11
26 | 42016 | 4O03 |  | DWR - Kure Beach | No |  |  | 0-25% | Next cycle - Spring 2021 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $2,187,500.37
27 | 42016 | 4O04 |  | DWR - Wrightsville Beach CSDR | No |  |  | 0-25% | Next cycle - Spring 2021 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $2,206,487.00
28 | 42016 | 4O05 |  | DWR - Ocean Isle CSDR | No |  |  | 0-25% | Next cycle - Spring 2021 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,040,016.76
29 | 42016 | 4O06 |  | DWR - Plannig Assistance to Communities | No |  |  |  | Ongoing | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $244,613.33
30 | 42016 | 4O07 |  | DWR - Wilmington Harbor DA Maintenance | No |  |  |  | Ongoing | 2236091.36 | General Fund | Receipts | Yes | On budget | No | Project Balance $3,670,358.64
31 | 42016 | 4O08 |  | DWR - Morehead City Maintenance | No |  |  |  | Ongoing | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,980,627.09
32 | 42016 | 4O09 |  | DWR - Surf City N Topsail CSRM | No |  |  | 0-25% | Spring 2023 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $12,500,000.00
33 | 42016 | 4O10 |  | DWR - Dan River Regional Water Supply | No |  |  | 0-25% | Spring 2022 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $34,000.00
34 | 42016 | 4O11 |  | DWR - Carteret County (Bogue Banks) CSRM | No |  |  | 0-25% | Spring 2023 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $2,567,320.08
35 | 42016 | 4O12 |  | DWR - Neuse River - Goldsboro | No |  |  | 51-75% | Spring 2022 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $333,500.00
36 | 42016 | 4O13 |  | DWR - Concord Stream Ecosystem Rest | No |  |  | 0-25% | Spring 2023 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,023,000.00
37 | 42016 | 4O14 |  | DWR - Lumberton Flood Damage Red | No |  |  | 51-75% | Fall 2022 | 0 | General Fund |  | Yes | On budget | No | Project Balance $125,000.00
38 | 42016 | 4O15 |  | DWR - B. Everette Jordan Reservoir Water | No |  |  |  | Ongoing | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,816,465.63
39 | 42016 | 4O16 |  | DWR - North Topsail Shoreline | No |  |  | 0-25% | Spring 2023 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,500,000.00
40 | 42016 | 4O17 |  | DWR - NCRS EQUIP / Stream Restoration | No |  |  |  | Ongoing | 0 | General Fund |  | Yes | On budget | No | Project Balance $2,064,698.97
41 | 42016 | 4O18 |  | DWR - State Local Projects | No |  |  |  | Ongoing | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $4,734,317.22
42 | 42016 | 4O19 |  | DWR - Water Resources Plan (SL 2010-143) | No |  |  | Complete | Completed | 20389.15 | General Fund |  | Yes | On budget | No | PROJECT COMPLETE - TO BE OFF NEXT REPORT
43 | 42016 | 4O20 |  | DWR - Cape Fear Lock & Dam #2 & #3 | No |  |  | 51-75% | Spring 2022 | 0 | General Fund |  | Yes | On budget | No | Project Balance $903,140.24
44 | 42016 | 4O21 |  | DCM - Masonboro Island Lot 9A | No |  |  |  |  | 0 | General Fund |  | Yes | On budget | No | Project Balance $4950.00; acquisition request on Council of State agenda Feb 2021
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172