## 04-01-20
Department: |  | Department of Environmental Quality
Report Date: |  | 04/01/20
CAPITAL IMPROVEMENT PROJECTS REPORT | [9 empty] | CAPITAL IMPROVEMENT PROJECTS REPORT
Project Identification | [5 empty] | Current Construction Phase |  |  |  | Funding and Sources |  |  | Adequacy of Funding |  |  | Comments
# | Budget Code | Fund Code | SCO Project ID# | Project Title | R&R Project? (Y/N) | Land Acquisition | Design Stages (Pick one from dropdown) | Construction Stage (Pick % complete from dropdown) | Projected Completion Date from Current Project Phase (Enter mo.&yr: XX/20XX) | Amt Expended Project to Date | Primary Funding Source (Pick one from dropdown) | Secondary Funding Source (Pick one from dropdown) | Is the project adequately funded? (Y/N) | How do current cost estimates compare to the project's initial authorized budget? | Will scope reductions be necessary to complete the project within its initial authorized budget? (Y/N) | Notes/Comments
1 | 40374 | 4X15 |  | DWR - Reedy Creek Renovations | Yes |  |  | 0-25% |  | 85919 | Debt Financed |  | Yes | On budget | No | Project Balance of $93,881.28
2 | 40616 | 4G21 |  | DWR - Neuse River Basin Study | No | - | - | Complete |  | 397783.1 | General Fund | Receipts | Yes | Under budget | No | Project Balance of -$3.00
3 | 40616 | 4G26 |  | DWR - Cow Channel Emergency Dredging | No | - | - | Complete |  | 2974322.22 | General Fund | Receipts | Yes | Under budget | No | Project Balance $735.00
4 | 41116 | 4M04 |  | DWR - Planning SL 2010-143 | No | - | - | - |  | 756690.7 | Receipts |  | Yes | On budget | No | Project Balance of $13,550.57
5 | 41216 | 4N05 |  | DWR - Corps Long Term MOA for Dredging | No | - | - | - |  | 3874267.2 | Receipts |  | Yes | On budget | No | Project Balance $672,000
6 | 41216 | 4N4M |  | DAQ - Lab Repair Water Dam | No | - | - | - |  | 3095 | General Fund |  | Yes | On budget | No | Project Balance $25,476
7 | 41316 | 4P30 | 13-10449-01A | ADM - R & R Innovation Center Building SEC | Yes | - | - | 76%-100% |  | 219257.14 | General Fund | Receipts | Yes | On budget | No | Project Balance $105731.92
8 | 41316 | 4P31 |  | ADM - Roof and HVAC Repair At Geo Office | Yes | - | - | Complete |  | 109002.27 | General Fund |  | Yes | Under budget | No | Project Balance $0 - Project Complete will NOT be on next quarter report
9 | 41416 | 4R06 |  | DWR -NRCS EQUIPMENT PROJECTS | No | - | - | - |  | 2000000 | General Fund |  | Yes | On budget | No | Project Balance $0 - Project Complete will NOT be on next quarter report
10 | 41416 | 4R08 |  | DWR -HOOKERTON STREAM REPAIR | No | - | - | - |  | 336783.97 | General Fund |  | Yes | On budget | No | Project Balance $73,216.03
11 | 41416 | 4R09 |  | DWR -STATE/LOCAL GRANTS | No | - | - | - |  | 935290.77 | General Fund |  | Yes | On budget | No | Project Balance $64,709.23
12 | 41474 | 4505 | 13-11114-01 | DWR-Replace Boilers Reedy Creek | Yes' | - | - | 76%-100% | Summer 2018 | 300142.21 | Debt Financed |  | Yes | Under budget | No | Project Balance $24,857.79
12 | 41516 | 4T16 |  | DWR - Planning SL 2010-143 | No | - | - | - |  | 9170.9 | General Fund |  | Yes | On budget | No | Project Balance $65,829.10
13 | 41516 | 4T17 |  | DWR - State Local Projects | No | - | - | - |  | 1206734.28 | General Fund | Receipts | Yes | On budget | No | Project Balance $187,438.98
14 | 41516 | 4T23 |  | ADM - HVAC Repairs DEQ Headquarters | Yes | - | - | 76%-100% |  | 10748.5 | General Fund |  | Yes | On budget | No | Project Balance $189,251.50
15 | 41616 | 4U07 |  | DWR - State Local Projects | No | - | - | - |  | 833966.38 | General Fund | Receipts | Yes | On budget | No | Project Balance $501,153.52
16 | 41616 | 4U08 |  | DWR - Cape Fear Lock & Dam #2 | No | - | - | - |  | 29315.92 | General Fund |  | Yes | On budget | No | Project Balance $470,684.08
17 | 41616 | 4U10 |  | DWR - EQIP | No | - | - | - |  | 1316036.4 | General Fund | Receipts | Yes | On budget | No | Project Balance $683,963.60
18 | 41616 | 4U11 |  | DWR - Town of Burgaw - Pender | No | - | - | - |  | 297387.78 | General Fund |  | Yes | On budget | No | Project Balance $49,612.22
19 | 41616 | 4U18 |  | DCM - Woodley Tract Acquisition | No | Complete | - | - |  | 308402.61 | Receipts |  | Yes | On budget | No | Project Balance $0 - Project Complete will NOT be on next quarter report
20 | 41616 | 4U20 |  | DMF - HVAC Controls System Upgrade | Yes | - | - | 76%-100% |  | 411461.61 | General Fund |  | Yes | On budget | No | Project Balance $21,934.41
21 | 41616 | 4U21 |  | DWR - Roof Replacement Reed Creek | Yes | - | Schematic Design (SD) | - | Spring 2019 | 215918 | General Fund | Receipts | Yes | On budget | No | Project Balance $7,876.70
22 | 41716 | 4V11 |  | DWR - EQUIP | No | - | - | - |  | 1831207.88 | General Fund |  | Yes | On budget | No | Project Balance $168,792.12
23 | 41716 | 4V12 |  | DWR - State Local Projects | No | - | - | - |  | 2251655.82 | General Fund | Receipts | Yes | On budget | No | Project Balance $717,280.18
24 | 41716 | 4V18 |  | DWR - Kuntz Farm Park Riverdale | No | - | - | - |  | 12050 | General Fund |  | Yes | On budget | No | Project Balance $237,950.00 - REPURPOSING TO 4Y16
25 | 41716 | 4V21 |  | DWR - Roof Replacement Reed Creek | Yes | - | Schematic Design (SD) | - | Winter 2021 | 0 | General Fund |  | Yes | On budget | No | Project Balance $567,100
26 | 41716 | 4V23 |  | DMF - Roof Maintenance Building | Yes | - | Design Development (DD) | - | Summer 2020 | 226695.95 | General Fund |  | Yes | On budget | No | Project Balance $236,304.05
27 | 41716 | 4V24 |  | DMF - Dock Structural Repairs | Yes | - | Design Development (DD) | - | Summer 2021 | 59521.05 | General Fund |  | Yes | On budget | No | Project Balance $ 621,495.81
28 | 41816 | 4Y01 |  | DWR - Princeville Flood | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,400,000
29 | 41816 | 4Y02 |  | DWR - Carolina Beach CSDR | No | - | - | - |  | 930531.84 | General Fund | Receipts | Yes | On budget | No | Project Balance $906,354.11 - increase from last quarter due to refund of unsued funds
30 | 41816 | 4Y03 |  | DWR - Kure Beach | No | - | - | - |  | 1423871.33 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,031,854.37 - increase from last quarter due to refund of unused funds
31 | 41816 | 4Y04 |  | DWR - Planning Assistance to Communities | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $171,397.10
32 | 41816 | 4Y05 |  | DWR - Bogue Banks CSRM | No | - | - | - |  | 173486.92 | General Fund | Receipts | Yes | On budget | No | Project Balance $28,513.08
33 | 41816 | 4Y06 |  | DWR - Wilmington Harbor DA Maintenance | No | - | - | - |  | 3392000 | General Fund | Receipts | Yes | On budget | No | Project Balance 3,630,549.85
34 | 41816 | 4Y07 |  | DWR - Surf City N Topsail CSRM | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $255,000
35 | 41816 | 4Y08 |  | DWR - West Onslow Beach CSRM | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $220,500
36 | 41816 | 4Y09 |  | DWR - Neuse River - Goldsboro | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $333,500
37 | 41816 | 4Y10 |  | DWR - Concord Stream Ecosystem Rest | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,023,000
38 | 41816 | 4Y11 |  | DWR - Manteo Old House Channel | No | - | - | - |  | 2738899.69 | General Fund | Receipts | Yes | On budget | No | Project Balance $0 - Project Complete will NOT be on next quarter report
39 | 41816 | 4Y12 |  | DWR - Lumberston Flood Damage Red | No | - | - | - |  | 0 | General Fund |  | Yes | On budget | No | Project Balance $125,000
40 | 41816 | 4Y13 |  | DWR - EQUIP | No | - | - | - |  | 396910.5 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,626,171.31
41 | 41816 | 4Y14 |  | DWR - Everett e Jordan | No | - | - | - |  | 209207.53 | General Fund | Receipts | Yes | On budget | No | Project Balance $141,900.00
42 | 41816 | 4Y16 |  | DWR - State Local Projects | No | - | - | - |  | 216849.83 | General Fund | Receipts | Yes | On budget | No | Project Balance $2,386,479.64
43 | 41816 | 4Y17 |  | DWR - Brunswick Ft Anderson | No | - | - | - |  | 0 | General Fund |  | Yes | On budget | No | Project Balance $487,000
44 | 41816 | 4Y18 |  | DWR - North Topsail Shoreline | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $ 1,500,000
45 | 41816 | 4Y19 |  | DWR - Lindsey BR Dam Repair & Stream Res | No | - | - | - |  | 55000 | General Fund |  | Yes | On budget | No | Project Balance $1,945,000.00
46 | 41816 | 4Y20 |  | DWR - Morehead City Maintenance | No | - | - | - |  | 300000 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,200,000
48 | 41816 | 4Y23 |  | DWR - Wrightsville Beach CSDR | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $2,206,487
49 | 41816 | 4Y25 |  | DWR - Cape Fear Lock & Dam #2 #3 Fish Ramp | No |  |  |  |  | 0 | General Fund |  | Yes | On budget | No | Project Balance $ 840,000
50 | 41816 | 4Y26 |  | DWR - Town of Rutherfordton Stream Restoration | No |  |  |  |  | 0 | General Fund |  | Yes | On budget | No | Project Balance $500,000
51 | 41816 | 4Y27 |  | DWR - Ararat River Greenway | No |  |  |  |  | 0 | General Fund |  | Yes | On budget | No | Project Balance $ 500,000
52 | 41816 | 4Y28 |  | DWR - Ocean Isle CSDR | No | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,040,016.76
53 | 41816 | 4Y29 |  | DWR - Reedy Creek Complex | Yes | - | - | - |  | 98460.64 | General Fund |  | Yes | On budget | No | Project Balance $1,277,619.20
54 | 41816 | 4Y32 |  | DWR - Modular Lab Building | Yes | - | - | - |  | 0 | General Fund | Receipts | Yes | On budget | No | R & R 2018-2020/Repurpose of Funds Project Balance $418,966.14
55 | 41916 | 4Z01 |  | DCM - Primland Tract | No |  |  |  |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $159,870.00