## Admin
DENR |  | Department of Environmental Quality | [7 empty] | Department:
Report Date: |  | 07/01/21 | [7 empty] | Report Date:
CAPITAL IMPROVEMENT PROJECTS REPORT | [9 empty] | CAPITAL IMPROVEMENT PROJECTS REPORT
Project Identification | [5 empty] | Current Construction Phase |  |  |  | Funding and Sources |  |  | Adequacy of Funding |  |  | Comments
# | Budget Code | Fund Code | SCO Project ID# | Project Title | R&R Project? (Y/N) | Land Acquisition | Design Stages (Pick one from dropdown) | Construction Stage (Pick % complete from dropdown) | Projected Completion Date from Current Project Phase (Enter mo.&yr: XX/20XX) | Amt Expended YTD | Primary Funding Source (Pick one from dropdown) | Secondary Funding Source (Pick one from dropdown) | Is the project adequately funded? (Y/N) | How do current cost estimates compare to the project's initial authorized budget? | Will scope reductions be necessary to complete the project within its initial authorized budget? (Y/N) | Notes/Comments
1 | 40374 | 4X15 |  | DWR - Reedy Creek Renovations | Yes |  |  | Complete |  | 162563.03 | Debt Financed |  | Yes | On budget | No | Project Balance of $6,881.26
2 | 41316 | 4P30 | 13-10449-01A | ADM - R & R Innovation Center Building SEC | Yes |  |  | 76%-100% |  | 304612 | General Fund | Receipts | Yes | On budget | No | Project Balance $20,376.26
3 | 41516 | 4T17 |  | DWR - State Local Projects | No |  |  |  |  | 1206734.28 | General Fund | Receipts | Yes | On budget | No | Project Balance $187,438.98
4 | 41616 | 4U07 |  | DWR - State Local Projects | No |  |  |  |  | 1018119.9 | General Fund | Receipts | Yes | On budget | No | Project Balance $317,000.00
5 | 41616 | 4U08 |  | DWR - Cape Fear Lock & Dam #2 | No |  |  |  |  | 29315.92 | General Fund |  | Yes | On budget | No | Project Balance $470,684.08
6 | 41616 | 4U10 |  | DWR - EQIP | No |  |  |  |  | 1824644.92 | General Fund | Receipts | Yes | On budget | No | Project Balance $175,355.08
7 | 41616 | 4U20 |  | DMF - HVAC Controls System Upgrade | Yes |  | Final Drawings/Bid (FD) | Complete | Summer 2020 | 432910.8 | General Fund |  | Yes | On budget | No | Project Balance $485.22
8 | 41716 | 4V11 |  | DWR - EQUIP | No |  |  |  |  | 1962292.19 | General Fund |  | Yes | On budget | No | Project Balance $37,707.81
9 | 41716 | 4V12 |  | DWR - State Local Projects | No |  |  |  |  | 2590580.83 | General Fund | Receipts | Yes | On budget | No | Project Balance $378,355.17
10 | 41716 | 4V21 |  | DWR - Roof Replacement Reed Creek | Yes |  | Final Drawings/Bid (FD) | Complete |  | 353163.5 | General Fund |  | Yes | On budget | No | Project Balance $213,936.60
12 | 41716 | 4V24 |  | DMF - Dock Structural Repairs | Yes |  | Final Drawings/Bid (FD) | 76%-100% | Summer 2021 | 212843.63 | General Fund |  | Yes | On budget | No | Project Balance $ 519,456.93
13 | 41816 | 4Y13 |  | DWR - EQUIP | No |  |  |  | Ongoing | 1862262.96 | General Fund | Receipts | Yes | On budget | No | Project Balance $160,818.85
14 | 41816 | 4Y14 |  | DWR - Everett e Jordan | No |  |  |  | Ongoing | 2025673.16 | General Fund | Receipts | Yes | On budget | No | Project Balance $15,167.24
15 | 41816 | 4Y16 |  | DWR - State Local Projects | No |  |  |  | Ongoing | 1261644.73 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,644,343.97
16 | 41816 | 4Y17 |  | DWR - Brunswick Ft Anderson | No |  |  | 51-75% | Spring 2021 | 380214.92 | General Fund |  | Yes | On budget | No | Project Balance $106,785.08
17 | 41816 | 4Y19 |  | DWR - Lindsey BR Dam Repair & Stream Res | No |  |  | 0-25% | Spring 2021 | 1939250 | General Fund |  | Yes | On budget | No | Project Balance $60,750.00
18 | 41816 | 4Y26 |  | DWR - Town of Rutherfordton Stream Restoration | No |  |  | 0-25% | Spring 2021 | 0 | General Fund |  | Yes | On budget | No | Project Balance $500,000
19 | 41816 | 4Y27 |  | DWR - Ararat River Greenway | No |  |  | 0-25% | Spring 2021 | 0 | General Fund |  | Yes | On budget | No | Project Balance $ 500,000
20 | 41816 | 4Y29 |  | DWR - Reedy Creek Complex | Yes |  | Final Drawings/Bid (FD) | 76%-100% | Winter 2021 | 994988.33 | General Fund |  | Yes | On budget | No | Project Balance $473,091.51
21 | 41816 | 4Y33 |  | DCM - Meter Point Tract | No |  |  | 76%-100% |  | 910984.11 | General Fund |  | Yes | On budget | No | Project Balance $-0- TO BE OFF REPORT NEXT QTR
22 | 41816 | 4Y34 |  | DWR- Reedy Creek Renovations | Yes |  | Final Drawings/Bid (FD) | 25-50% |  | 349834.08 | General Fund | Receipts | Yes | On budget | No | Projedct Balance $100,010.39
23 | 41916 | 4Z01 |  | DCM - Primland Tract | No |  |  |  |  | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $159,870.00; easement requirement being worked with Dept of Defense
24 | 42016 | 4O01 |  | DWR - Princeville Flood | No |  |  | 0-25% | Spring 2024 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $3,465,000.00
25 | 42016 | 4O02 |  | DWR - Carolina Beach CSDR | No |  |  | 0-25% | Next cycle - Spring 2021 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,754,946.65
26 | 42016 | 4O03 |  | DWR - Kure Beach | No |  |  | 0-25% | Next cycle - Spring 2021 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $2,187,500.37
27 | 42016 | 4O04 |  | DWR - Wrightsville Beach CSDR | No |  |  | 0-25% | Next cycle - Spring 2021 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $2,206,487.00
28 | 42016 | 4O05 |  | DWR - Ocean Isle CSDR | No |  |  | 0-25% | Next cycle - Spring 2021 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,040,016.76
29 | 42016 | 4O06 |  | DWR - Plannig Assistance to Communities | No |  |  |  | Ongoing | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $244,613.33
30 | 42016 | 4O07 |  | DWR - Wilmington Harbor DA Maintenance | No |  |  |  | Ongoing | 2236091.36 | General Fund | Receipts | Yes | On budget | No | Project Balance $3,670,358.64
31 | 42016 | 4O08 |  | DWR - Morehead City Maintenance | No |  |  |  | Ongoing | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,980,627.09
32 | 42016 | 4O09 |  | DWR - Surf City N Topsail CSRM | No |  |  | 0-25% | Spring 2023 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $12,500,000.00
33 | 42016 | 4O10 |  | DWR - Dan River Regional Water Supply | No |  |  | 0-25% | Spring 2022 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $34,000.00
34 | 42016 | 4O11 |  | DWR - Carteret County (Bogue Banks) CSRM | No |  |  | 0-25% | Spring 2023 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $2,567,320.08
35 | 42016 | 4O12 |  | DWR - Neuse River - Goldsboro | No |  |  | 51-75% | Spring 2022 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $333,500.00
36 | 42016 | 4O13 |  | DWR - Concord Stream Ecosystem Rest | No |  |  | 0-25% | Spring 2023 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,023,000.00
37 | 42016 | 4O14 |  | DWR - Lumberton Flood Damage Red | No |  |  | 51-75% | Fall 2022 | 0 | General Fund |  | Yes | On budget | No | Project Balance $125,000.00
38 | 42016 | 4O15 |  | DWR - B. Everette Jordan Reservoir Water | No |  |  |  | Ongoing | 151400.65 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,807,642.37
39 | 42016 | 4O16 |  | DWR - North Topsail Shoreline | No |  |  | 0-25% | Spring 2023 | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $1,500,000.00
40 | 42016 | 4O17 |  | DWR - NCRS EQUIP / Stream Restoration | No |  |  |  | Ongoing | 0 | General Fund |  | Yes | On budget | No | Project Balance $2,064,698.97
41 | 42016 | 4O18 |  | DWR - State Local Projects | No |  |  |  | Ongoing | 0 | General Fund | Receipts | Yes | On budget | No | Project Balance $4,734,317.22
43 | 42016 | 4O20 |  | DWR - Cape Fear Lock & Dam #2 & #3 | No |  |  | 51-75% | Spring 2022 | 0 | General Fund |  | Yes | On budget | No | Project Balance $903,140.24
44 | 42016 | 4O21 |  | DCM - Masonboro Island Lot 9A | No |  |  |  |  | 0 | General Fund |  | Yes | On budget | No | Project Balance $4950.00; Council of State approved Feb 2021, project scheduled to close summer 2021
45 | 42016 | 4O22 |  | DMF-R&R Main Campus Chiller Replacement | Yes |  |  | Complete |  | 129500 | General Fund |  |  | On budget |  | Project Balance $120,500.00
46 | 42016 | 4O23 |  | DWR-R&R Reedy Creek Lab Campus Renovations | Yes |  | Design Development (DD) | 0-25% | 2022-12-01 | 53647.5 | General Fund |  |  | On budget |  | Project Balance $1,596,352.50
47 | 42016 | 4O24 |  | DWR-R&R Reedy Creek Lab Generator | Yes |  | Final Drawings/Bid (FD) | 0-25% | 2021-12-01 | 21320 | General Fund |  |  | On budget |  | Project Balance $478,680.00
48 | 42016 | 4O25 |  | DMF-R&R Shellfish San Lab HVAC System | Yes |  | Final Drawings/Bid (FD) | 0-25% | 2021-12-01 | 0 | General Fund |  |  | On budget |  | Project Balance $175,000.00
49 | 42016 | 4O26 |  | DWR-R&R Reedy Creek Lab Freezer | Yes |  |  |  |  | 0 | General Fund |  |  | On budget
50 | 42016 | 4O27 |  | ADM - Green Square Renovations | No |  | Final Drawings/Bid (FD) | 0-25% | 2021-09-01 | 0 | General Fund |  |  | On budget | No | Project Balance $50,000.00
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## DropDowns
-
Schematic Design (SD)
Design Development (DD)
Construction Drawings (CD)
Final Drawings/Bid (FD)
-
0-25%
25-50%
51-75%
76%-100%
Complete
-
Yes
No
-
General Fund
Receipts
Debt Financed
Self-Liquidating/Revenue Bonds
-
General Fund
Receipts
Debt Financed
Self-Liquidating/Revenue Bonds
-
On budget
Under budget
Over budget
-
General Fund
Receipt
-
Appraisal
Price negotiations
COS approval process
Closing
Complete