# Mining Commission Rule Readoption Timeline

- Staff/Mining Stakeholder Group to complete draft rule amendments by October 31, 2024.

  - The Mining Commission and DEQ have put together a Stakeholder group composed of industry, environmental, and governmental representatives.  The Mining Rules Stakeholder group meets every other week, alternating virtual and in person, to draft new rules and modify existing rules.  While the group has been meeting since November 2023 time was needed to walk the group through the NC Mining Act of 1971 and current Department procedures before work could begin on the rulemaking process.  Work on drafting and revising rules began in January 2024, and the group has made significant modifications to existing rules as well as drafting new rules in order to improve and streamline the regulatory process.  The group anticipates completing its work by the end of October 2024.

- Rules Committee review of draft amendments by early November 2024.

- Rules Committee to hold meeting to discuss draft rule amendments by mid-December 2024.

- Staff to develop fiscal analysis and have OSBM approval between December 2024 and March 2025.

- Rules Committee review of draft fiscal analysis by early April 2025.

- Rules Committee to hold meeting to discuss fiscal analysis by late April 2025.

- Mining Commission to approve the draft rules and fiscal analysis to proceed to public comment at its regularly scheduled July 2025 meeting.

- Rules filed for publication in the NC Register by end of July 2025.

- Earliest hearing date can occur on or after mid-August 2025.

- End of public comment period by early September 2025.

- Staff to develop Hearing Officer’s Report (HOR) between early September 2025 and early December 2025.

- Rules Committee to review draft HOR by mid-January 2026.

- Rules Committee to hold meeting to discuss the HOR by end of March 2026.

- Mining Commission to adopt the rules, approve the HOR including the Regulatory Impact Analysis (RIA) at its regularly scheduled July 2026 meeting.