North Carolina

County of Typical

In the matter of Town of Typicalville	)

Pretreatment Permit No. 0006	)

held by Will Plateit Metal Finishers, Inc.	)

CONSENT ORDER AND COMPLIANCE SCHEDULE

Pursuant to provisions of the Sewer User Ordinance of the Town of Typicalville, this Consent Order is made effective the 1st day of March, 1998, between Will Plateit Metal Finishers, Inc. (hereinafter the "User") and the Town of Typcialville (hereinafter the "Town").

The User and Town hereby stipulate and agree as follows:

1.	User holds Town of Typicalville Pretreatment Permit No. 0006 (hereinafter the "Permit", which shall refer to User's existing permit and any subsequent renewals or modifications thereof) for the operations of existing pretreatment units and discharges from said treatment works into the Town's sewer system.

2.	User has been unable to meet the permit limitations for Cadmium (Cd) set forth in its Permit.

3.	Achievement of these limits will require resolution of existing problems in the present treatment train and possibly, development of alternative solutions to alleviate noncompliance, including but not limited to the construction of additional pretreatment facilities as well as the preparation of plans and specifications as necessary.

4.	User hereby agrees to do and perform all of the following:

a.	Meet and comply with all terms and conditions of the Permit (except as modified by the Order) provided, however, subject to the terms and conditions of the Consent Order, the following shall apply:

Parameter	Daily Max (mg/L)	Monitoring Frequency 	Detection Limit

Cadmium (Cd)	0.13	Weekly	0.002 mg/L

b.	Unless and until Compliance is achieved, the User will undertake activities necessary to bring the User into Compliance in accordance with the following schedule:

COMPLIANCE SCHEDULE

| Activities | Deadline for Completion |
| --- | --- |
| (i) Prepare an Engineering Report of process alternatives and/or pollution prevention/waste minimization alternative designed to achieve Compliance | April 1, 1998 |
| (ii) Complete Pilot Studies or waste minimization studies and identify alternatives chosen to achieve Compliance | July 1, 1998 |
| (iii) If required, submit necessary drawings and information to obtain any necessary permits and/or authorization to construct from the Town of Typicalville | September 1, 1998 |
| (iv) Begin construction and/or implement identified process alternative(s), pollution prevention, and waste minimization alternatives. | December 1, 1998 |
| (v) Complete identified construction/pollution prevention/ waste minimization alternatives and/or process alternatives. | March 1, 1999 |
| (vi) Complete analysis of implemented changes, including daily monitoring from April 1st to May 1st and make necessary modifications to optimize and obtain full operational status. | June 1, 1999 |
| (vii) Achieve compliance with final (IUP) limit 0.07 mg/L | July 1, 1999 |

c.	User shall perform each of the activities set forth in subparagraph (b) on or before the dates established thereby unless such dates are extended by agreement of User and the Town may request such extensions for good cause, and the Town will not unreasonably withhold its consent to such extensions.

d.	User shall submit a comprehensive written report within five (5) days following each milestone date specified in subparagraph (b). Each such report shall be in narrative form, shall state in detail the activities undertaken since the last report to achieve Compliance, and shall indicate whether User has met the due date for the relevant milestone established in this Consent Order. If any report contains notice of failure to meet a milestone date, the report shall also include a statement explaining the cause of the failure, any remedial actions taken, and the probability of meeting the next milestone.

During any period of construction, User shall submit on or before the 10th day of each month, detailed construction progress reports stating therein in narrative form the work performed during the month and the percentage of completion of the project.

All reports required by the Consent Order shall be submitted to the Town by Certified Mail, Return Receipt Requested, addressed to:

Director of Public Utilities

Town of Typicalville

PO Box 123

Typcialville, NC  12345

e.	The User shall pay the Town $1,000, no later than February 27, 1998, for the Significant Non-Compliance during the July through December 1997 reporting period.

f.	Any violation of the terms of this Consent Order shall subject the User to the enforcement authority outlined in the Ordinance. Such action may include, but is not limited to such fines, penalties and assessments as may be set forth in the Code of Ordinance of the Town of Typicalville, as amended from time to time.

In lieu of other penalties, the following stipulated penalties shall apply for violations of the User's limits or failure to meet a milestone date under this Consent Order, or failure to achieve full compliance with Consent Order.

Violation of limits		$200 per day, per violation

Failure to collected required samples, meet

compliance schedule deadlines, required reports,

or other milestone dates contained herein	$200 per day, per violation

Failure to achieve full compliance with Final

IUP limit at expiration of Order		$1,000 per day

g.	Once Compliance is achieved, this Consent Order shall terminate and all obligations hereunder except any obligation to pay identified moneys to the Town shall expire. Upon termination of this Order, the User shall be subject to all terms of the Permit.

h.	In the performance of activities under this Consent Order, User must otherwise follow the procedures, rules, regulations, ordinances, and statutes of the Town, State, and Federal governments as they may apply to User. Nothing contained herein shall be construed as a waiver thereof by the Town.

Signed on this 26th day of January 1998.

USER:			Will Plateit Metal Finishers, Inc.

William B Plateit

BY:

President

TITLE:

TOWN:			Town of Typicalville

# Jane Wastewater

BY:

TITLE:			Director of Public Utilities

This Order expires July 11, 1999.