## Quantities and Credits
Table 1. Mitigation Site (ID-95021) Project Mitigation Quantities and Credits
Original
| Mitigation |  | Original | Original | Original
| Plan | As-Built | Mitigation | Restoration | Mitigation
Project Segment | Ft/Ac | Ft/Ac | Category | Level | Ratio (X:1) | Credits | Comments
Stream
DRT-W-R1_1 | 1606 | 1798 | Cool | R | 1 | 1606
DRT-W-R1_3 | 2497 | 2656 | Warm | R | 1 | 2497
DRT-W-R2_4 | 958 | 958 | Cold | R | 1 | 958
DRT-E-R1_7 | 1259 | 1351 | Warm | R | 1 | 1259
DRT-E-R2-3_8 | 589 | 589 | Warm | R | 1 | 589
SWB-R2_13 | 76 | 191 | Warm | EI | 1.5 | 50.667
SWB-R3_14 | 279 | 279 | Cold | R | 1 | 279
SWB-R3_15 | 114 | 114 | Warm | R | 4 | 28.5
MB_Head_17 | 411 | 411 | Cool | HQP | 1 | 411
MB-R1-R2_18 | 1507 | 1507 | Warm | R | 1 | 1507
SEB-R1_20 | 483 | 483 | Warm | R | 1 | 483
SEB-R3_22 | 621 | 673 | Cool | R | 1 | 621
[5 empty] | Total: | 10289.167
Wetland
West_Group_1 | 16.292 | 16.608 | CM | RH | 1.5 | 10.861
West_Group_2 | 38.55 | 37.238 | R | REE | 1 | 38.55
West_Group_U_3 | 1.528 | 1.528 | R | R | 4 | 0.382
West_Group_4 | 1.166 | 1.166 | R | E | 2 | 0.583
East_Group_5 | 3.815 | 3.949 | NR | P | 10 | 0.382
[5 empty] | Total: | 50.758
Project Credits
Restoration Level | Stream | Stream |  | Riparian | Non-Rip | Coastal
Restoration Level | Warm | Cool | Cold | Wetland | Wetland | Marsh
Restoration | 6363.5 | 2227 | 1237 | 0.382 | 0 | 0
Re-establishment |  |  |  | 38.55 | 0 | 0
Rehabilitation |  |  |  | 0 | 0 | 10.861
Enhancement |  |  |  | 0.583 | 0 | 0
Enhancement I | 50.667 | 0 | 0
Enhancement II | 0 | 0 | 0
Creation |  |  |  | 0 | 0 | 0
Preservation | 0 | 0 | 0 | 0 | 0.382
Totals | 6414.167 | 2227 | 1237 | 39.515 | 0.382 | 10.861
Total Stream Credit | 10289.167
Total Wetland Credit | 50.758
| Wetland Mitigation Category |  |  | Restoration Level
| CM | Coastal Marsh |  | HQP | High Quality Preservation
| R | Riparian |  | P | Preservation
| NR | Non-Riparian |  | E | Wetland Enhancement - Veg and Hydro
|  |  |  | EII | Stream Enhancement II
|  |  |  | EI | Stream Enhancement I
|  |  |  | C | Wetland Creation
|  |  |  | RH | Wetland Rehabilitation - Veg and Hydro
|  |  |  | REE | Wetland Re-establishment Veg and Hydro
|  |  |  | R | Restoration

## Project Attribute Table
Project Attribute Table
Project Name
County
Project Area (acres)
Project Coordinates (latitude and longitude decimal degrees)
Project Watershed Summary Information
Physiographic Province
River Basin
USGS Hydrologic Unit 8-digit
DWR Sub-basin
Project Drainage Area (acres)
Project Drainage Area Percentage of Impervious Area
Land Use Classification
Reach Summary Information
Parameters | Reach 1 | Reach 2 | Reach 3
Pre-project length (feet)
Post-project (feet)
Valley confinement (Confined, moderately confined, unconfined)
Drainage area (acres)
Perennial, Intermittent, Ephemeral
NCDWR Water Quality Classification
Dominant Stream Classification (existing)
Dominant Stream Classification (proposed)
Dominant Evolutionary class (Simon) if applicable
Wetland Summary Information
Parameters | Wetland 1 | Wetland 2 | Wetland 3
Pre-project (acres)
Post-project (acres)
Wetland Type (non-riparian, riparian)
Mapped Soil Series
Soil Hydric Status
Regulatory Considerations
Parameters | Applicable? | Resolved? | Supporting Docs?
Water of the United States - Section 404
Water of the United States - Section 401
Endangered Species Act
Historic Preservation Act
Coastal Zone Management Act (CZMA or CAMA)
Essential Fisheries Habitat

## Morph Table Essential Param
Provide Project Name, EEP Identification Number, River Basin and CU
Reach ID
A full morphology table can be provided as part of the digital submission, but the paramters below
are viewed as essential and should be included in the report body
Parameter | Existing Condition | Reference Condition | Proposed
Valley Width (ft)
Contributing Drainage Area (acres)
Channel/Reach Classification
Discharge Width (ft)
Discharge Depth (ft)
Discharge Area (ft2)
Discharge Velocity (ft/s)
Discharge (cfs)
Water Surface Slope
Sinuosity
Width/Depth Ratio
Bank Height Ratio
Entrenchment Ratio
d16 / d35 / d50 / d84 / d95 / dip / disp (mm)

## XS Data & Plots
Project and Reach Information | [9 empty] | Cross Section Information
Project Name: |  | XYZ Creek | [5 empty] | Installer Cross Section ID: |  |  | 22-XS2
Project ID: |  | 1234 | [5 empty] | EEP XS Database ID: |  |  | EEP Use
Reach ID: |  | Reach 22 | [5 empty] | Installation Organization: |  |  | Firm X
Reach Type: |  | B4c | [5 empty] | Installation Personnel: |  |  | CC, DD, EE
[8 empty] | Installation Date: |  |  | 2014-01-01
[8 empty] | Cross Section Type: |  |  | Riffle
[10 empty] | Drainage Area: | 1.8
Survey Information |  |  | Elevation | BS | FS |  |  |  |  | Survey Information |  |  | Elevation | BS | FS |  |  | Survey Information |  |  | Elevation | BS | FS |  |  | Survey Information |  |  | Elevation | BS | FS |  |  | Survey Information |  |  | Elevation | BS | FS |  |  | Survey Information |  |  | Elevation | BS | FS
| Survey Date: | MY0 2/28/2012 | [8 empty] | Survey Date: | [7 empty] | Survey Date: | [7 empty] | Survey Date: | [7 empty] | Survey Date: | [7 empty] | Survey Date:
| Benchmark ID: | TP1 | 917.75 | 4.11 | [6 empty] | Benchmark ID: | TP1 | 917.75 | [5 empty] | Benchmark ID: | TP1 | 917.75 | [5 empty] | Benchmark ID: | TP1 | 917.75 | [5 empty] | Benchmark ID: | TP1 | 917.75 | [5 empty] | Benchmark ID: | TP1 | 917.75
| Height of Instrument: |  | 921.86 | [7 empty] | Height of Instrument: |  | 917.75 | [5 empty] | Height of Instrument: |  | 917.75 | [5 empty] | Height of Instrument: |  | 917.75 | [5 empty] | Height of Instrument: |  | 917.75 | [5 empty] | Height of Instrument: |  | 917.75
| Survey Organization: | Firm X | [8 empty] | Survey Organization: | [7 empty] | Survey Organization: | [7 empty] | Survey Organization: | [7 empty] | Survey Organization: | [7 empty] | Survey Organization:
| Survey Personnel: | CC,DD | [8 empty] | Survey Personnel: | [7 empty] | Survey Personnel: | [7 empty] | Survey Personnel: | [7 empty] | Survey Personnel: | [7 empty] | Survey Personnel:
| Survey Conditions: | 80F; Sunnty | [8 empty] | Survey Conditions: | [7 empty] | Survey Conditions: | [7 empty] | Survey Conditions: | [7 empty] | Survey Conditions: | [7 empty] | Survey Conditions:
| Project Phase: | MY0 2/28/2012 | [8 empty] | Project Phase: | [7 empty] | Project Phase: | [7 empty] | Project Phase: | [7 empty] | Project Phase: | [7 empty] | Project Phase:
| Note: | [10 empty] | Note: | [5 empty] | Note: | [7 empty] | Note: | [8 empty] | Note: | [7 empty] | Note:
[5 empty] | Bkf Hydraulic Geom | [9 empty] | Bkf Hydraulic Geom | [7 empty] | Bkf Hydraulic Geom | [7 empty] | Bkf Hydraulic Geom | [7 empty] | Bkf Hydraulic Geom | [7 empty] | Bkf Hydraulic Geom
TOB | BKF | STA | FS | EL | Depth | Width | Area |  |  | TOB | BKF | STA | FS | EL | Depth | Width | Area | TOB | BKF | STA | FS | EL | Depth | Width | Area | TOB | BKF | STA | FS | EL | Depth | Width | Area | TOB | BKF | STA | FS | EL | Depth | Width | Area | TOB | BKF | STA | FS | EL | Depth | Width | Area
TLP |  | 0 | 5.09 | 916.77 | 0 | 0 | 0 |  | 4.59 |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
BLP |  | 0 | 5.55 | 916.31 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 1 | 5.55 | 916.31 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
TLB | LTOB | 6 | 5.66 | 916.2 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 7.1 | 5.95 | 915.91 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 8.6 | 6.65 | 915.21 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 10.2 | 7.63 | 914.23 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 12 | 8.1 | 913.76 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 15 | 8.17 | 913.69 | 0 | 3 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 18.8 | 8.31 | 913.55 | 0.14 | 3.8 | 0.266 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
| LBKF | 20.2 | 8.17 | 913.69 | 0 | 1.4 | 0.098 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 23 | 8.31 | 913.55 | 0.14 | 2.8 | 0.196 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 24.3 | 8.51 | 913.35 | 0.34 | 1.3 | 0.312 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 25.8 | 8.8 | 913.06 | 0.63 | 1.5 | 0.7275 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 27.8 | 8.86 | 913 | 0.69 | 2 | 1.32 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 27.8 | 9.6 | 912.26 | 1.43 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 29.2 | 9.81 | 912.05 | 1.64 | 1.4 | 2.149 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 31.8 | 10.08 | 911.78 | 1.91 | 2.6 | 4.615 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
LEW |  | 34.6 | 10.34 | 911.52 | 2.17 | 2.8 | 5.712 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 36.3 | 10.45 | 911.41 | 2.28 | 1.7 | 3.7825 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 37 | 10.54 | 911.32 | 2.37 | 0.7 | 1.6275 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 38 | 10.43 | 911.43 | 2.26 | 1 | 2.315 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 39 | 10.5 | 911.36 | 2.33 | 1 | 2.295 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 41 | 10.49 | 911.37 | 2.32 | 2 | 4.65 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 43 | 10.61 | 911.25 | 2.44 | 2 | 4.76 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 44 | 10.3 | 911.56 | 2.13 | 1 | 2.285 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 46 | 10.69 | 911.17 | 2.52 | 2 | 4.65 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
| THW | 47 | 10.74 | 911.12 | 2.57 | 1 | 2.545 |  | 916.32 |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 49.5 | 10.63 | 911.23 | 2.46 | 2.5 | 6.2875 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
REW |  | 49.7 | 10.2 | 911.66 | 2.03 | 0.2 | 0.449 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 54 | 9.55 | 912.31 | 1.38 | 4.3 | 7.3315 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 57.3 | 8.94 | 912.92 | 0.77 | 3.3 | 3.5475 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
| RBKF | 60.5 | 8.1 | 913.76 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 63.8 | 7.69 | 914.17 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 65 | 7.77 | 914.09 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 67.4 | 7.23 | 914.63 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 69.3 | 7.12 | 914.74 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 71 | 6.64 | 915.22 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 73.1 | 5.65 | 916.21 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
RTB |  | 74.1 | 4.7 | 917.16 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 75 | 4.55 | 917.31 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
|  | 77 | 4.39 | 917.47 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
BRP |  | 78 | 4.3 | 917.56 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
RLP |  | 78 | 3.8 | 918.06 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
EL: 0; Bkf Hydraulic Geom Depth: 0; Bkf Hydraulic Geom Width: 0; Bkf Hydraulic Geom Area: 0 | [6 empty] | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A |  |  |  |  | 0 | 0 | 0 | #N/A
| Feature | Type | Wfpa | LBKF | RBKF | ELbkf | Wbkf | Dbkf | W/D | Abkf | Dmax | ER | BHR
MY0 2/28/2012 | RIF | F | 72 | 20.2 | 60.5 | 913.69 | 40.3 | 1.5365 | 26.2284 | 61.921 | 2.57 | 1.7866 | 1.95
| RIF | F | 100 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
| RIF | F | 100 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
| RIF | F | 100 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
| RIF | F | 100 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
| RIF | F | 100 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
FS: elev; Bkf Hydraulic Geom Depth: area; Bkf Hydraulic Geom Width: d; Bkf Hydraulic Geom Area: shear | velocity | power | width | Q
|  | 0.5 | 90 | 6.5 | 6.5 | 0.5 | 0.08112 | 0.4736 | 0.038418 | 13 | 3.0784
|  | 1 | 90.5 | 7 | 13.5 | 0.96429 | 0.15645 | 0.73378 | 0.1148 | 14 | 9.906
|  | 1.5 | 91 | 7.5 | 21 | 1.4 | 0.22714 | 0.94084 | 0.2137 | 15 | 19.7576
|  | 2 | 91.5 | 7.5 | 28.5 | 1.9 | 0.30826 | 1.1533 | 0.3555 | 15 | 32.8682
|  | 2.5 | 92 | 7.5 | 36 | 2.4 | 0.38938 | 1.3476 | 0.52473 | 15 | 48.5145
|  | 3 | 92.5 | 9 | 45 | 2.5 | 0.4056 | 1.3848 | 0.56168 | 18 | 62.3162
|  | 3.5 | 93 | 11.5 | 56.5 | 2.4565 | 0.39855 | 1.3687 | 0.54549 | 23 | 77.3317
|  | 4 | 93.5 | 13 | 69.5 | 2.6731 | 0.43368 | 1.448 | 0.62797 | 26 | 100.6362
|  | 4.5 | 94 | 14.5 | 84 | 2.8966 | 0.46994 | 1.5276 | 0.71789 | 29 | 128.3203
|  | 5 | 94.5 | 15.5 | 99.5 | 3.2097 | 0.52074 | 1.6358 | 0.85183 | 31 | 162.7643
|  | 5.5 | 95 | 17 | 116.5 | 3.4265 | 0.55591 | 1.7087 | 0.94987 | 34 | 199.0608
|  |  | dmean = | 4.1281
|  |  | r= | 2.6626
|  |  | Qbkf= | 87.69
|  |  | n= | 0.10106
Note on I4: gmmelia: If different
Note on K9: gmmelia: square miles
Note on A29: Melia, Gregory: Top of Left Bank
Note on B29: Melia, Gregory: Lower of the 2 banks (TLB and RTB)
Note on A65: Melia, Gregory: Top of right Bank

## grain size analysis
The data entry table is set up for 1/2 phi-size intervals. If you have phi-size interval data, leave the intervening intervals blank.
Particle ; Monitoring YR4
Creek Mitigation Project, EEP# 12345 |  |  |  |  | 2014-03-15
PROJECT:
REACH/LOCATION: |  | XS 3
FEATURE: |  | Riffle
|  |  | 2014 |  |  | Distribution
MATERIAL | PARTICLE | SIZE (mm) | Total | Class % | % Cum | Plot Size (mm)
Silt/Clay | Silt / Clay | < .063 |  |  | 0% | 0.063
Sand | Very Fine | .063 - .125 |  |  | 0% | 0.125
| Fine | .125 - .25 |  |  | 0% | 0.25
| Medium | .25 - .50 |  |  | 0% | 0.5
| Coarse | .50 - 1.0 |  |  | 0% | 1
| Very Coarse | 1.0 - 2.0 |  |  | 0% | 2
Gravel | Very Fine | 2.0 - 2.8 |  |  | 0% | 2.8
| Very Fine | 2.8 - 4.0 | 1 | 0.9709% | 0.9709% | 4
| Fine | 4.0 - 5.6 |  |  | 0.9709% | 5.6
| Fine | 5.6 - 8.0 | 4 | 3.883% | 4.854% | 8
| Medium | 8.0 - 11.0 | 2 | 1.942% | 6.796% | 11
| Medium | 11.0 - 16.0 | 5 | 4.854% | 11.65% | 16
| Coarse | 16 - 22.6 | 6 | 5.825% | 17.48% | 22.6
| Coarse | 22.6 - 32 | 9 | 8.738% | 26.21% | 32
| Very Coarse | 32 - 45 | 18 | 17.48% | 43.69% | 45
| Very Coarse | 45 - 64 | 21 | 20.39% | 64.08% | 64
Cobble | Small | 64 - 90 | 23 | 22.33% | 86.41% | 90
| Small | 90 - 128 | 10 | 9.709% | 96.12% | 128
| Large | 128 - 180 | 4 | 3.883% | 100% | 180
| Large | 180 - 256 |  |  | 100% | 256
Boulder | Small | 256 - 362 |  |  | 100% | 362
| Small | 362 - 512 |  |  | 100% | 512
| Medium | 512 - 1024 |  |  | 100% | 1024
| Large-Very Large | 1024 - 2048 |  |  | 100% | 2048
Bedrock | Bedrock | > 2048 |  |  | 100% | 5000
Total % of whole count |  |  | 103 | 100%
Summary Data
Channel materials
|  | D16 = | 20.71 | D84 = | 86.75
|  | D35 = | 37.98 | D95 = | 122.92
|  | D50 = | 50.18 | D100 = | 128-180

## Raw GW and Precip Data
Offset should be specified and uncorrected data should be submitted
Project:
Project ID:
Wetland Component: | Wetland 1
Growing Season: | March 15-November 19
Units | Inches
Gauge Type: | Groundwater |  | Groundwater |  | Groundwater |  | Groundwater |  | Groundwater |  | Groundwater |  | Groundwater |  | Groundwater |  | Groundwater |  | Groundwater |  | Rain
| Gauge ID : | test-1 | Gauge ID: | KBMG-2 | Gauge | KBMG-3 | Gauge | KBMG-4 | Gauge | KBMG-5 | Gauge | KBMG-6 | Gauge | KBMG-6 | Gauge | KBMG-6 | Gauge | KBMG-6 | Gauge | KBMG-6 | Gauge | RG1
| Offset | 0 | Offset | 0 | Offset | 0 | Offset | 0 | Offset | 0 | Offset | 0 | Offset | 0 | Offset | 0 | Offset | 0 | Offset | 0 | Source: | Site
Date | Depth |  | Depth |  | Depth |  | Depth |  | Depth |  | Depth |  | Depth |  | Depth |  | Depth |  | Depth |  | Amount
2004-01-01 | -41.7
2004-01-02 | -41.8
2004-01-03 | -41.8
2004-01-04 | -41.8
2004-01-05 | -41.8
2004-01-06 | -41.7
2004-01-07 | -41.8
2004-01-08 | -41.8
2004-01-09 | -41.8
2004-01-10 | -41.7
2004-01-11 | -41.9
2004-01-12 | -41.8
2004-01-13 | -41.8
2004-01-14 | -41.9
2004-01-15 | -41.9
2004-01-16 | -41.9
2004-01-17 | -41.9
2004-01-18 | -41.9
2004-01-19 | -42
2004-01-20 | -41.9
2004-01-21 | -41.8
2004-01-22 | -41.9
2004-01-23 | -41.9
2004-01-24 | -41.9
2004-01-25 | -41.9
2004-01-26 | -41.8
2004-01-27 | -41.9
2004-01-28 | -41.9
2004-01-29 | -41.8
2004-01-30 | -41.9
2004-01-31 | -41.8
2004-02-01 | -41.8
2004-02-02 | -41.8
2004-02-03 | -41.8
2004-02-04 | -41.8
2004-02-05 | -41.8
2004-02-06 | -41.9
2004-02-07 | -41.9
2004-02-08 | -41.9
2004-02-09 | -41.8
2004-02-10 | -41.8
2004-02-11 | -41.8
2004-02-12 | -41.9
2004-02-13 | -41.9
2004-02-14 | -42
2004-02-15 | -41.9
2004-02-16 | -41.9
2004-02-17 | -41.9
2004-02-18 | -41.9
2004-02-19 | -41.9
2004-02-20 | -41.9
2004-02-21 | -41.8
2004-02-22 | -41.8
2004-02-23 | -41.9
2004-02-24 | -41.9
2004-02-25 | -41.8
2004-02-26 | -41.9
2004-02-27 | -41.9
2004-02-28 | -41.9
2004-02-29 | -41.8
2004-03-01 | -41.8
2004-03-02 | -41.8
2004-03-03 | -41.9
2004-03-04 | -41.9
2004-03-05 | -41.9 |  | -20.1 |  | -0.7 |  | -1.2
2004-03-06 | -41.8 |  | -11.4 |  | 0.5 |  | -1.4 | [13 empty] | 0.02
2004-03-07 | -41.9 |  | -7.5 |  | -1.4 |  | -2.2 | [13 empty] | 0
2004-03-08 | -41.8 |  | -5.5 |  | -2.5 |  | -4 | [13 empty] | 0
2004-03-09 | -41.8 |  | -6.3 |  | -4.2 |  | -5.7 | [13 empty] | 0
2004-03-10 | -41.8 |  | -7.5 |  | -5.2 |  | -6.6 | [13 empty] | 0
2004-03-11 | -41.8 |  | -9.6 |  | -6.6 |  | -8.3 |  | -14.5 | [11 empty] | 0
2004-03-12 | -41.8 |  | -10.2 |  | -5.6 |  | -9.3 |  | -14.6 | [11 empty] | 0
2004-03-13 | -41.8 |  | -11.4 |  | -7.8 |  | -11.5 |  | -17.1 | [11 empty] | 0
2004-03-14 | -41.8 |  | -13.6 |  | -9.3 |  | -12.8 |  | -18.6 | [11 empty] | 0
2004-03-15 | -41.8 |  | -13.9 |  | -7.5 |  | -12.7 |  | -18.5 | [11 empty] | 0
2004-03-16 | -41.8 |  | -7.7 |  | -3.5 |  | -8.3 |  | -12.7 | [11 empty] | 0.36
2004-03-17 | -41.8 |  | -8.7 |  | -3.8 |  | -8.4 |  | -11.7 | [11 empty] | 0.01
2004-03-18 | -41.8 |  | -10.7 |  | -5.9 |  | -10.1 |  | -13.7 | [11 empty] | 0
2004-03-19 | -41.8 |  | -12.1 |  | -6.4 |  | -11.1 |  | -14.9 | [11 empty] | 0.04
2004-03-20 | -41.9 |  | -14.9 |  | -8.6 |  | -13.4 |  | -17.3 | [11 empty] | 0
2004-03-21 | -41.9 |  | -12.2 |  | -3.8 |  | -11.4 |  | -15.3 | [11 empty] | 0.16
2004-03-22 | -41.8 |  | -13.7 |  | -7.3 |  | -13.7 |  | -18.3 | [11 empty] | 0
2004-03-23 | -41.8 | E | -16.1 |  | -10.5 |  | -16.6 |  | -20.6 | [11 empty] | 0
2004-03-24 | -41.7 | E | -18.1 |  | -11.7 |  | -17.8 |  | -21.6 | [11 empty] | 0
2004-03-25 | -41.6 | E | -19.3 |  | -12.4 |  | -18.7 |  | -22.6 | [11 empty] | 0
2004-03-26 | -41.6 |  | -19.9 |  | -12.8 |  | -19.1 |  | -23.3 | [11 empty] | 0
2004-03-27 | -41.7 |  | -19.3 |  | -12.4 |  | -18.9 |  | -24.1 | [11 empty] | 0
2004-03-28 | -41.6 |  | -18.1 |  | -12 |  | -18.8 |  | -24.9 | [11 empty] | 0
2004-03-29 | -41.7 |  | -18 |  | -14.1 |  | -20.3 |  | -26.4 | [11 empty] | 0
2004-03-30 | -41.7 | I | -17.6 |  | -14.9 |  | -20.6 |  | -27.3 | [11 empty] | 0.01
2004-03-31 | -41.6 | I | -15.2 |  | -14.7 |  | -20.1 |  | -27.7 | [11 empty] | 0.33
2004-04-01 | -41.6 | I | -15 |  | -14.6 |  | -20.2 |  | -28 | [11 empty] | 0.06
2004-04-02 | -41.6 | I | -15.8 |  | -16 |  | -21.1 |  | -28.7 | [11 empty] | 0
2004-04-03 | -41.6 | I | -17.1 |  | -17.9 |  | -22.3 |  | -29.5 | [11 empty] | 0
2004-04-04 | -41.7 | I | -18 |  | -18.7 |  | -22.4 |  | -30 | [11 empty] | 0
2004-04-05 | -41.8 | I | -19.8 |  | -21 |  | -24.3 |  | -31.3 | [11 empty] | 0
2004-04-06 | -41.8 | I | -21.4 |  | -22.9 |  | -25.5 |  | -32.5 | [11 empty] | 0
2004-04-07 | -41.8 | I | -22.3 |  | -23.1 |  | -25.5 |  | -32.8 | [11 empty] | 0
2004-04-08 | -41.8 | I | -22.4 |  | -23.1 |  | -25.6 |  | -33.2 | [11 empty] | 0
2004-04-09 | -41.8 | I | -22.7 |  | -24.1 |  | -26.7 |  | -34.2 | [11 empty] | 0
2004-04-10 | -41.8 | I | -23.8 |  | -25.7 |  | -27.9 |  | -35.1 | [11 empty] | 0
2004-04-11 | -41.8 |  | -24.5 |  | -26.5 |  | -28.6 |  | -35.8 | [11 empty] | 0
2004-04-12 | -41.8 |  | -25.2 |  | -27.4 |  | -29 |  | -36.5 | [11 empty] | 0.33
2004-04-13 | -41.8 |  | -24.5 |  | -27.5 |  | -29.1 |  | -36.7 | [11 empty] | 0.31
2004-04-14 | -41.8 |  | -16.9 |  | -27.3 |  | -29.4 |  | -36.6 | [11 empty] | 0.02
2004-04-15 | -17.5 |  | -21.5 |  | -29 |  | -30.7 |  | -37.9 | [11 empty] | 0
2004-04-16 | -18.5 |  | -24.8 |  | -30.1 |  | -31.6 |  | -38.8 | [11 empty] | 0
2004-04-17 | -19.6 |  | -26.9 |  | -30.7 |  | -32.1 |  | -39.5 | [11 empty] | 0
2004-04-18 | -20.4 |  | -28.4 |  | -31.1 |  | -32.6 |  | -40 | [11 empty] | 0
2004-04-19 | -20.7 |  | -29.5 |  | -31.5 |  | -33.1 |  | -40.3 | [11 empty] | 0
2004-04-20 | -21 |  | -29.8 |  | -31.5 |  | -33.3 |  | -40 | [11 empty] | 0
2004-04-21 | -21.4 |  | -29.9 |  | -31.8 |  | -33.8 |  | -40.2 |  | -26 |  | -26 |  | -26 |  | -26 |  | -26 |  | 0
2004-04-22 | -21.8 |  | -30.4 |  | -32.4 |  | -34.8 |  | -40.6 |  | -27.5 |  | -27.5 |  | -27.5 |  | -27.5 |  | -27.5 |  | 0
2004-04-23 | -7.6 |  | -31.1 |  | -33.3 |  | -35.8 |  | -40.7 |  | -28.6 |  | -28.6 |  | -28.6 |  | -28.6 |  | -28.6 |  | 0
2004-04-24 | -15.1 |  | -31.9 |  | -34 |  | -36.6 |  | -40.7 |  | -29.6 |  | -29.6 |  | -29.6 |  | -29.6 |  | -29.6 |  | 0
2004-04-25 | -18.3 |  | -32.8 |  | -34.8 |  | -37.6 |  | -41.1 |  | -30.9 |  | -30.9 |  | -30.9 |  | -30.9 |  | -30.9 |  | 0
2004-04-26 | -19.2 |  | -33.7 |  | -35.2 |  | -38.2 |  | -41.1 |  | -31.2 |  | -31.2 |  | -31.2 |  | -31.2 |  | -31.2 |  | 0.14
2004-04-27 | -20.5 |  | -34.3 |  | -35.4 |  | -38.8 |  | -41.1 |  | -31.7 |  | -31.7 |  | -31.7 |  | -31.7 |  | -31.7 |  | 0.01
2004-04-28 | -21.8 |  | -35.4 |  | -36.1 |  | -39.7 |  | -41.2 |  | -33.7 |  | -33.7 |  | -33.7 |  | -33.7 |  | -33.7 |  | 0
2004-04-29 | -22.2 |  | -36.6 |  | -37 |  | -40.1 |  | -41.2 |  | -35.3 |  | -35.3 |  | -35.3 |  | -35.3 |  | -35.3 |  | 0
2004-04-30 | -23 |  | -37.6 |  | -37.6 |  | -40.2 |  | -41.2 |  | -35.8 |  | -35.8 |  | -35.8 |  | -35.8 |  | -35.8 |  | 0
2004-05-01 | -23.3 |  | -38.6 |  | -37.9 |  | -41.1 |  | -41.2 |  | -35.8 |  | -35.8 |  | -35.8 |  | -35.8 |  | -35.8 |  | 0.3
2004-05-02 | -19.2 |  | -11.3 |  | -20.5 |  | -34.7 |  | -36.2 |  | -23.5 |  | -23.5 |  | -23.5 |  | -23.5 |  | -23.5 |  | 2.09
2004-05-03 | -5.9 |  | 3.1 |  | 3.3 |  | -9.4 |  | -20.3 |  | 3.4 |  | 3.4 |  | 3.4 |  | 3.4 |  | 3.4 |  | 0.06
2004-05-04 | -5.9 |  | 0.3 |  | 1.2 |  | 1.1 |  | -25.4 |  | 2.6 |  | 2.6 |  | 2.6 |  | 2.6 |  | 2.6 |  | 0
2004-05-05 | -7.5 |  | -3.6 |  | 0.1 |  | 0.1 |  | -27.5 |  | 1.8 |  | 1.8 |  | 1.8 |  | 1.8 |  | 1.8 |  | 0
2004-05-06 | -9 |  | -5.3 |  | -1 |  | -1.4 |  | -28.9 |  | 1.2 |  | 1.2 |  | 1.2 |  | 1.2 |  | 1.2 |  | 0
2004-05-07 | -10.9 |  | -5.8 |  | -2.5 |  | -3.8 |  | -29.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2004-05-08 | -14 |  | -8.9 |  | -5.6 |  | -7.4 |  | -30.6 |  | -2 |  | -2 |  | -2 |  | -2 |  | -2 |  | 0
2004-05-09 | -16.5 |  | -11.4 |  | -7.3 |  | -11 |  | -31.4 |  | -3.4 |  | -3.4 |  | -3.4 |  | -3.4 |  | -3.4 |  | 0
2004-05-10 | -17.6 |  | -13.6 |  | -9.3 |  | -15.5 |  | -32.2 |  | -4.7 |  | -4.7 |  | -4.7 |  | -4.7 |  | -4.7 |  | 0
2004-05-11 | -18.8 |  | -15.8 |  | -11.1 |  | -19.2 |  | -33 |  | -6 |  | -6 |  | -6 |  | -6 |  | -6 |  | 0
2004-05-12 | -19.5 |  | -17.5 |  | -13 |  | -21.7 |  | -34 |  | -7.6 |  | -7.6 |  | -7.6 |  | -7.6 |  | -7.6 |  | 0
2004-05-13 | -18.7 |  | -18.9 |  | -14.7 |  | -23.5 |  | -34.9 |  | -8.9 |  | -8.9 |  | -8.9 |  | -8.9 |  | -8.9 |  | 0
2004-05-14 | -12.5 |  | -20 |  | -16.2 |  | -25.1 |  | -35.8 |  | -10 |  | -10 |  | -10 |  | -10 |  | -10 |  | 0
2004-05-15 | -17 |  | -21.1 |  | -17.6 |  | -26.3 |  | -36.7 |  | -11 |  | -11 |  | -11 |  | -11 |  | -11 |  | 0
2004-05-16 | -20.2 |  | -22.1 |  | -18.9 |  | -27.7 |  | -37.9 |  | -12.4 |  | -12.4 |  | -12.4 |  | -12.4 |  | -12.4 |  | 0
2004-05-17 | -21.4 |  | -23.2 |  | -20.2 |  | -28.9 |  | -39.5 |  | -14 |  | -14 |  | -14 |  | -14 |  | -14 |  | 0
2004-05-18 | -15.2 |  | -24.2 |  | -21.3 |  | -30 |  | -40.5 |  | -14.8 |  | -14.8 |  | -14.8 |  | -14.8 |  | -14.8 |  | 0
2004-05-19 | -17.7 |  | -24.9 |  | -22.2 |  | -30.9 |  | -40.6 |  | -14.5 |  | -14.5 |  | -14.5 |  | -14.5 |  | -14.5 |  | 0
2004-05-20 | -18.6 |  | -25.6 |  | -23 |  | -31.6 |  | -41.1 |  | -15.5 |  | -15.5 |  | -15.5 |  | -15.5 |  | -15.5 |  | 0
2004-05-21 | -17.1 |  | -26.3 |  | -23.8 |  | -32.3 |  | -41.1 |  | -16.6 |  | -16.6 |  | -16.6 |  | -16.6 |  | -16.6 |  | 0
2004-05-22 | -5.5 |  | -26.8 |  | -24.5 |  | -33.1 |  | -41.1 |  | -17.1 |  | -17.1 |  | -17.1 |  | -17.1 |  | -17.1 |  | 0
2004-05-23 | -6.7 |  | -27.3 |  | -25.2 |  | -33.9 |  | -41.1 |  | -17.8 |  | -17.8 |  | -17.8 |  | -17.8 |  | -17.8 |  | 0.05
2004-05-24 | -10.5 |  | -27.9 |  | -25.9 |  | -34.8 |  | -41.1 |  | -19.1 |  | -19.1 |  | -19.1 |  | -19.1 |  | -19.1 |  | 0
2004-05-25 | -14.8 |  | -28.6 |  | -26.7 |  | -35.7 |  | -41.2 |  | -20.4 |  | -20.4 |  | -20.4 |  | -20.4 |  | -20.4 |  | 0
2004-05-26 | -16.9 |  | -29.2 |  | -27.4 |  | -36.6 |  | -41.2 |  | -21.6 |  | -21.6 |  | -21.6 |  | -21.6 |  | -21.6 |  | 0
2004-05-27 | -18.9 |  | -30 |  | -28.1 |  | -37.5 |  | -41.2 |  | -22.9 |  | -22.9 |  | -22.9 |  | -22.9 |  | -22.9 |  | 0
2004-05-28 | -21.2 |  | -30.6 |  | -28.9 |  | -38.5 |  | -41.2 |  | -24.3 |  | -24.3 |  | -24.3 |  | -24.3 |  | -24.3 |  | 0.02
2004-05-29 | -21.7 |  | -31.3 |  | -29.6 |  | -39.6 |  | -41.2 |  | -27.1 |  | -27.1 |  | -27.1 |  | -27.1 |  | -27.1 |  | 0
2004-05-30 | -5 |  | -32 |  | -30.2 |  | -39.8 |  | -41.2 |  | -28.5 |  | -28.5 |  | -28.5 |  | -28.5 |  | -28.5 |  | 0.01
2004-05-31 | -5.6 |  | -32.5 |  | -30.7 |  | -39.8 |  | -41.2 |  | -29.5 |  | -29.5 |  | -29.5 |  | -29.5 |  | -29.5 |  | 0.13
2004-06-01 | -8.3 |  | -33.1 |  | -31.2 |  | -39.8 |  | -41.2 |  | -31.2 |  | -31.2 |  | -31.2 |  | -31.2 |  | -31.2 |  | 0
2004-06-02 | -12.7 |  | -33.9 |  | -31.9 |  | -39.8 |  | -41.2 |  | -32.6 |  | -32.6 |  | -32.6 |  | -32.6 |  | -32.6 |  | 0
2004-06-03 | -5.2 |  | -34.7 |  | -32.4 |  | -39.8 |  | -41.3 |  | -34.7 |  | -34.7 |  | -34.7 |  | -34.7 |  | -34.7 |  | 0
2004-06-04 | -8 |  | -35.1 |  | -32.9 |  | -39.7 |  | -41.2 |  | -35.4 |  | -35.4 |  | -35.4 |  | -35.4 |  | -35.4 |  | 0.23
2004-06-05 | -13.5 |  | -35.9 |  | -33.5 |  | -40.5 |  | -41.2 |  | -36.4 |  | -36.4 |  | -36.4 |  | -36.4 |  | -36.4 |  | 0
2004-06-06 | -4.9 |  | -36.5 |  | -34.1 |  | -40.5 |  | -41.2 |  | -37.5 |  | -37.5 |  | -37.5 |  | -37.5 |  | -37.5 |  | 0
2004-06-07 | -5 |  | -37.3 |  | -34.8 |  | -40.5 |  | -41.2 |  | -38.4 |  | -38.4 |  | -38.4 |  | -38.4 |  | -38.4 |  | 0
2004-06-08 | -8.2 |  | -38.2 |  | -35.4 |  | -40.5 |  | -41.2 |  | -39.4 |  | -39.4 |  | -39.4 |  | -39.4 |  | -39.4 |  | 0
2004-06-09 | -13.8 |  | -39.6 |  | -36 |  | -40.5 |  | -41.3 |  | -39.8 |  | -39.8 |  | -39.8 |  | -39.8 |  | -39.8 |  | 0.96
2004-06-10 | -16.4 |  | -20.6 |  | -27.4 |  | -37.8 |  | -41.1 |  | -37.3 |  | -37.3 |  | -37.3 |  | -37.3 |  | -37.3 |  | 0
2004-06-11 | -18 |  | -23.9 |  | -29 |  | -39.7 |  | -41.2 |  | -36.9 |  | -36.9 |  | -36.9 |  | -36.9 |  | -36.9 |  | 0
2004-06-12 | -19.7 |  | -26.4 |  | -30.2 |  | -39.7 |  | -41.2 |  | -38 |  | -38 |  | -38 |  | -38 |  | -38 |  | 0
2004-06-13 | -21.2 |  | -29 |  | -31.5 |  | -39.7 |  | -41.2 |  | -40.1 |  | -40.1 |  | -40.1 |  | -40.1 |  | -40.1 |  | 0.04
2004-06-14 | -22.7 |  | -30.9 |  | -32.3 |  | -40.4 |  | -41.2 |  | -40.1 |  | -40.1 |  | -40.1 |  | -40.1 |  | -40.1 |  | 0.17
2004-06-15 | -22.4 |  | -32.1 |  | -33.2 |  | -40.4 |  | -41.2 |  | -40.6 |  | -40.6 |  | -40.6 |  | -40.6 |  | -40.6 |  | 0.04
2004-06-16 | -21.6 |  | -33.2 |  | -34.1 |  | -40.4 |  | -41.2 |  | -40.6 |  | -40.6 |  | -40.6 |  | -40.6 |  | -40.6 |  | 0.06
2004-06-17 | -22.5 |  | -34.3 |  | -34.9 |  | -40.4 |  | -41.2 |  | -40.7 |  | -40.7 |  | -40.7 |  | -40.7 |  | -40.7 |  | 0
2004-06-18 | -24 |  | -35.1 |  | -35.8 |  | -40.4 |  | -41.2 |  | -40.7 |  | -40.7 |  | -40.7 |  | -40.7 |  | -40.7 |  | 0
2004-06-19 | -25.3 |  | -36.1 |  | -36.5 |  | -40.4 |  | -41.3 |  | -40.7 |  | -40.7 |  | -40.7 |  | -40.7 |  | -40.7 |  | 0.99
2004-06-20 | -26 |  | -17.6 |  | -25.8 |  | -39.7 |  | -41.2 |  | -39.8 |  | -39.8 |  | -39.8 |  | -39.8 |  | -39.8 |  | 0.01
2004-06-21 | -26.6 |  | -22.1 |  | -28 |  | -40.4 |  | -41.2 |  | -40 |  | -40 |  | -40 |  | -40 |  | -40 |  | 0.9
2004-06-22 | -27.2 |  | -15.4 |  | -24.5 |  | -39.3 |  | -41.2 |  | -28.1 |  | -28.1 |  | -28.1 |  | -28.1 |  | -28.1 |  | 0.48
2004-06-23 | -27.9 |  | -11.5 |  | -20.3 |  | -38.2 |  | -41.1 |  | -20 |  | -20 |  | -20 |  | -20 |  | -20 |  | 1.45
2004-06-24 | -28.8 |  | -0.1 |  | -1.7 |  | -8.9 |  | -10.4 |  | 3.3 |  | 3.3 |  | 3.3 |  | 3.3 |  | 3.3 |  | 0.16
2004-06-25 | -29.3 |  | -0.3 |  | -2.4 |  | -15.3 |  | -13.6 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 0.28
2004-06-26 | -30 |  | 0.8 |  | -1.9 |  | -14.3 |  | -7.7 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 0.08
2004-06-27 | -26.4 |  | -1.1 |  | -4.2 |  | -18.1 |  | -13.7 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 0.25
2004-06-28 | -28.1 |  | 1.2 |  | -1.6 |  | -19.1 |  | -11 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 0
2004-06-29 | -23.4 |  | -1.3 |  | -4.3 |  | -21.4 |  | -16 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 0
2004-06-30 | -25.3 |  | -3.6 |  | -10.4 |  | -23 |  | -21.5 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 0.3
2004-07-01 | -26.4 |  | -0.5 |  | -6 |  | -23.5 |  | -20.6 |  | 3.2 |  | 3.2 |  | 3.2 |  | 3.2 |  | 3.2 |  | 0.01
2004-07-02 | -27.2 |  | -3.2 |  | -8.7 |  | -24.3 |  | -21.2 |  | 3.6 |  | 3.6 |  | 3.6 |  | 3.6 |  | 3.6 |  | 0.07
2004-07-03 | -28.5 |  | -5.5 |  | -10.8 |  | -25 |  | -23.7 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 0.02
2004-07-04 | -27.5 |  | -7.5 |  | -12.5 |  | -25.2 |  | -25.8 |  | 3.2 |  | 3.2 |  | 3.2 |  | 3.2 |  | 3.2 |  | 0.31
2004-07-05 | -22.4 |  | -4.5 |  | -11.9 |  | -26.5 |  | -26.6 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 0.01
2004-07-06 | -23 |  | -8.1 |  | -13 |  | -27.5 |  | -27.2 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 0
2004-07-07 | -25 |  | -10 |  | -15.1 |  | -28.5 |  | -28.4 |  | 0.7 |  | 0.7 |  | 0.7 |  | 0.7 |  | 0.7 |  | 0
2004-07-08 | -26.6 |  | -12 |  | -17.1 |  | -29.4 |  | -30.1 |  | -4 |  | -4 |  | -4 |  | -4 |  | -4 |  | 0
2004-07-09 | -28 |  | -14.3 |  | -19.5 |  | -30.5 |  | -32.3 |  | -7.4 |  | -7.4 |  | -7.4 |  | -7.4 |  | -7.4 |  | 0
2004-07-10 | -29 |  | -16.7 |  | -21.2 |  | -31.5 |  | -34.1 |  | -10 |  | -10 |  | -10 |  | -10 |  | -10 |  | 0
2004-07-11 | -30.5 |  | -18.8 |  | -22.4 |  | -32.5 |  | -35.7 |  | -13.9 |  | -13.9 |  | -13.9 |  | -13.9 |  | -13.9 |  | 0.01
2004-07-12 | -28.6 |  | -20.6 |  | -23.5 |  | -33.4 |  | -36.9 |  | -16.2 |  | -16.2 |  | -16.2 |  | -16.2 |  | -16.2 |  | 0.01
2004-07-13 | -29.4 |  | -22.1 |  | -24.4 |  | -34.3 |  | -37.7 |  | -17.4 |  | -17.4 |  | -17.4 |  | -17.4 |  | -17.4 |  | 0
2004-07-14 | -30.7 |  | -23.3 |  | -25 |  | -35.3 |  | -38.7 |  | -18.5 |  | -18.5 |  | -18.5 |  | -18.5 |  | -18.5 |  | 0
2004-07-15 | -31.6 |  | -24.6 |  | -25.8 |  | -36.4 |  | -39.4 |  | -20.5 |  | -20.5 |  | -20.5 |  | -20.5 |  | -20.5 |  | 0
2004-07-16 | -32.4 |  | -25.9 |  | -26.8 |  | -37.4 |  | -39.9 |  | -22.6 |  | -22.6 |  | -22.6 |  | -22.6 |  | -22.6 |  | 0
2004-07-17 | -32.6 |  | -27.2 |  | -27.7 |  | -38.7 |  | -40.1 |  | -24.2 |  | -24.2 |  | -24.2 |  | -24.2 |  | -24.2 |  | 0.31
2004-07-18 | -30.3 |  | -28.1 |  | -28 |  | -39.3 |  | -40 |  | -25.6 |  | -25.6 |  | -25.6 |  | -25.6 |  | -25.6 |  | 0.01
2004-07-19 | -31.5 |  | -29.2 |  | -28.9 |  | -39.7 |  | -40.1 |  | -27.2 |  | -27.2 |  | -27.2 |  | -27.2 |  | -27.2 |  | 0.03
2004-07-20 | -32.3 |  | -30.3 |  | -29.7 |  | -39.7 |  | -40.1 |  | -28.7 |  | -28.7 |  | -28.7 |  | -28.7 |  | -28.7 |  | 0.01
2004-07-21 | -32.2 |  | -31.3 |  | -30.6 |  | -39.8 |  | -40.1 |  | -30.7 |  | -30.7 |  | -30.7 |  | -30.7 |  | -30.7 |  | 0
2004-07-22 | -32.7 |  | -32.2 |  | -31.4 |  | -40.4 |  | -40.6 |  | -31.6 |  | -31.6 |  | -31.6 |  | -31.6 |  | -31.6 |  | 0
2004-07-23 | -32.7 |  | -33 |  | -32.1 |  | -40.5 |  | -40.6 |  | -32.5 |  | -32.5 |  | -32.5 |  | -32.5 |  | -32.5 |  | 0
2004-07-24 | -32.9 |  | -33.8 |  | -33 |  | -40.5 |  | -40.6 |  | -33.7 |  | -33.7 |  | -33.7 |  | -33.7 |  | -33.7 |  | 0
2004-07-25 | -32.9 |  | -34.7 |  | -34 |  | -40.5 |  | -40.6 |  | -35.2 |  | -35.2 |  | -35.2 |  | -35.2 |  | -35.2 |  | 0
2004-07-26 | -33 |  | -35.6 |  | -35 |  | -40.5 |  | -40.7 |  | -36.4 |  | -36.4 |  | -36.4 |  | -36.4 |  | -36.4 |  | 0
2004-07-27 | -33 |  | -36.4 |  | -35.8 |  | -39.8 |  | -40.7 |  | -37.4 |  | -37.4 |  | -37.4 |  | -37.4 |  | -37.4 |  | 0.75
2004-07-28 | -33.1 |  | -23.5 |  | -30.9 |  | -39.8 |  | -39.9 |  | -36.3 |  | -36.3 |  | -36.3 |  | -36.3 |  | -36.3 |  | 0.01
2004-07-29 | -33.2 |  | -27.7 |  | -32.1 |  | -39.8 |  | -40.1 |  | -37.6 |  | -37.6 |  | -37.6 |  | -37.6 |  | -37.6 |  | 0.17
2004-07-30 | -33.3 |  | -30.6 |  | -33 |  | -39.9 |  | -40.2 |  | -38.9 |  | -38.9 |  | -38.9 |  | -38.9 |  | -38.9 |  | 0.01
2004-07-31 | -33 |  | -32.4 |  | -34.1 |  | -38.8 |  | -40.3 |  | -39.7 |  | -39.7 |  | -39.7 |  | -39.7 |  | -39.7 |  | 0.29
2004-08-01 | -33.3 |  | -33.7 |  | -34.8 |  | -39.5 |  | -40.3 |  | -39.7 |  | -39.7 |  | -39.7 |  | -39.7 |  | -39.7 |  | 0.03
2004-08-02 | -33.3 |  | -34.6 |  | -35.5 |  | -32.5 |  | -40.4 |  | -40.4 |  | -40.4 |  | -40.4 |  | -40.4 |  | -40.4 |  | 0.93
2004-08-03 | -33 |  | -16 |  | -29.1 |  | -34.6 |  | -35.8 |  | -28.8 |  | -28.8 |  | -28.8 |  | -28.8 |  | -28.8 |  | 0.03
2004-08-04 | -33.2 |  | -20.7 |  | -30.8 |  | -35.8 |  | -35.5 |  | -29.2 |  | -29.2 |  | -29.2 |  | -29.2 |  | -29.2 |  | 0
2004-08-05 | -33.3 |  | -23.9 |  | -31.7 |  | -35.4 |  | -37.1 |  | -29.4 |  | -29.4 |  | -29.4 |  | -29.4 |  | -29.4 |  | 0.25
2004-08-06 | -33.4 |  | -25.5 |  | -32.5 |  | -37.1 |  | -39.7 |  | -29.7 |  | -29.7 |  | -29.7 |  | -29.7 |  | -29.7 |  | 0.03
2004-08-07 | -33.4 |  | -28.1 |  | -33.7 |  | -38.4 |  | -39.9 |  | -31.7 |  | -31.7 |  | -31.7 |  | -31.7 |  | -31.7 |  | 0
2004-08-08 | -33.5 |  | -30.1 |  | -34.8 |  | -39.6 |  | -40.1 |  | -32.4 |  | -32.4 |  | -32.4 |  | -32.4 |  | -32.4 |  | 0
2004-08-09 | -33.5 |  | -31.6 |  | -35.8 |  |  |  | -40.1 |  | -34.3 |  | -34.3 |  | -34.3 |  | -34.3 |  | -34.3 |  | 0.01
2004-08-10 | -33.5 |  | -31.3 |  | -36.6 |  |  |  | -40.2 |  | -36.1 |  | -36.1 |  | -36.1 |  | -36.1 |  | -36.1 |  | 0
2004-08-11 | -33.6 |  | -32.2 |  | -37.4 |  |  |  | -40.3 |  | -37.4 |  | -37.4 |  | -37.4 |  | -37.4 |  | -37.4 |  | 0
2004-08-12 | -33.6 |  | -33 |  | -38.2 |  |  |  | -40.4 |  | -38.2 |  | -38.2 |  | -38.2 |  | -38.2 |  | -38.2 |  | 0.38
2004-08-13 | -33.6 |  | -33.2 |  | -37.3 |  |  |  | -40.4 |  | -39.5 |  | -39.5 |  | -39.5 |  | -39.5 |  | -39.5 |  | 0.18
2004-08-14 | -33.7 |  | 2 |  | -7.1 |  |  |  | 1.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 1.58
2004-08-15 | -33.6 |  | 3.5 |  | 2.7 |  |  |  | 2.8 |  | 3.9 |  | 3.9 |  | 3.9 |  | 3.9 |  | 3.9 |  | 1.05
2004-08-16 | -33.7 |  | 4.3 |  | 4.4 |  |  |  | 1.9 |  | 4.1 |  | 4.1 |  | 4.1 |  | 4.1 |  | 4.1 |  | 0.01
2004-08-17 | -33.7 |  | 2.3 |  | 2.1 |  |  |  | -1.4 |  | 3.8 |  | 3.8 |  | 3.8 |  | 3.8 |  | 3.8 |  | 0
2004-08-18 | -33.6 |  | 0.3 |  | 1.2 |  |  |  | -5.2 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 0
2004-08-19 | -33.5 |  | -2.5 |  | 0.3 |  |  |  | -12 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 0
2004-08-20 | -33.5 |  | -6.6 |  | -1.1 |  |  |  | -18.2 |  | 2.3 |  | 2.3 |  | 2.3 |  | 2.3 |  | 2.3 |  | 0
2004-08-21 | -33.5 |  | -8.8 |  | -2.5 |  |  |  | -21.9 |  | 1.3 |  | 1.3 |  | 1.3 |  | 1.3 |  | 1.3 |  | 0.14
2004-08-22 | -33.5 |  | -10.7 |  | -2.5 |  |  |  | -25.4 |  | 1.9 |  | 1.9 |  | 1.9 |  | 1.9 |  | 1.9 |  | 0.01
2004-08-23 | -33.5 |  | -13.1 |  | -6.8 |  |  |  | -28 |  | 0.2 |  | 0.2 |  | 0.2 |  | 0.2 |  | 0.2 |  | 0
2004-08-24 | -33.6 |  | -15.3 |  | -9.8 |  |  |  | -30.4 |  | -2.9 |  | -2.9 |  | -2.9 |  | -2.9 |  | -2.9 |  | 0
2004-08-25 | -33.7 |  | -17.4 |  | -12.7 |  |  |  | -32.8 |  | -6.5 |  | -6.5 |  | -6.5 |  | -6.5 |  | -6.5 |  | 0
2004-08-26 | -33.7 |  | -19.3 |  | -15.8 |  |  |  | -34.7 |  | -9.9 |  | -9.9 |  | -9.9 |  | -9.9 |  | -9.9 |  | 0
2004-08-27 | -33.7 |  | -21 |  | -18.3 |  |  |  | -36.1 |  | -13.4 |  | -13.4 |  | -13.4 |  | -13.4 |  | -13.4 |  | 0.01
2004-08-28 | -33.5 |  | -22.4 |  | -20.3 |  |  |  | -36.8 |  | -15 |  | -15 |  | -15 |  | -15 |  | -15 |  | 0
2004-08-29 | -33.5 |  | -23.6 |  | -21.7 |  |  |  | -37.5 |  | -16.6 |  | -16.6 |  | -16.6 |  | -16.6 |  | -16.6 |  | 2.55
2004-08-30 | -33.6 |  | 4.5 |  | 4.5 |  |  |  | 3.3 |  | 4.2 |  | 4.2 |  | 4.2 |  | 4.2 |  | 4.2 |  | 0.81
2004-08-31 | -33.6 |  | 4.6 |  | 4.6 |  |  |  | 3 |  | 4.6 |  | 4.6 |  | 4.6 |  | 4.6 |  | 4.6 |  | 0.24
2004-09-01 | -33.7 |  | 4.5 |  | 4.5 |  |  |  | 2.5 |  | 4.6 |  | 4.6 |  | 4.6 |  | 4.6 |  | 4.6 |  | 0
2004-09-02 | -33.1 |  | 3.3 |  | 3.1 |  |  |  | 1.3 |  | 4.5 |  | 4.5 |  | 4.5 |  | 4.5 |  | 4.5 |  | 0.01
2004-09-03 | -15 |  | 1.8 |  | 1.8 |  |  |  | -1.1 |  | 3.8 |  | 3.8 |  | 3.8 |  | 3.8 |  | 3.8 |  | 0
2004-09-04 | -29.6 |  | 0.7 |  | 1.3 |  |  |  | -3.4 |  | 3.6 |  | 3.6 |  | 3.6 |  | 3.6 |  | 3.6 |  | 0
2004-09-05 | -33.5 |  | -0.7 |  | 0.8 |  |  |  | -6.4 |  | 3.3 |  | 3.3 |  | 3.3 |  | 3.3 |  | 3.3 |  | 0.01
2004-09-06 | -33.5 |  | -3.9 |  | 0.3 |  |  |  | -10.6 |  | 2.9 |  | 2.9 |  | 2.9 |  | 2.9 |  | 2.9 |  | 0.23
2004-09-07 | -33.7 |  | 1.4 |  | 1.3 |  |  |  | -4.5 |  | 3.7 |  | 3.7 |  | 3.7 |  | 3.7 |  | 3.7 |  | 4.86
2004-09-08 | -33.7 |  | 4.4 |  | 4.4 |  |  |  | 4.2 |  | 4.3 |  | 4.3 |  | 4.3 |  | 4.3 |  | 4.3 |  | 2.16
2004-09-09 | -33.6 |  | 4.5 |  | 4.5 |  |  |  | 4.6 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 0
2004-09-10 | -33.6 |  | 4.7 |  | 4.6 |  |  |  | 3 |  | 5.1 |  | 5.1 |  | 5.1 |  | 5.1 |  | 5.1 |  | 0
2004-09-11 | -33.6 |  | 3.7 |  | 4.2 |  |  |  | 2.6 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 0
2004-09-12 | -33.5 |  | 2.4 |  | 2.3 |  |  |  | 1.6 |  | 4.6 |  | 4.6 |  | 4.6 |  | 4.6 |  | 4.6 |  | 0
2004-09-13 | -33.4 |  | 1.3 |  | 1.7 |  |  |  | 0.2 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 0.01
2004-09-14 | -33.5 |  | 1.4 |  | 1.5 |  |  |  | -0.3 |  | 3.9 |  | 3.9 |  | 3.9 |  | 3.9 |  | 3.9 |  | 0.03
2004-09-15 | -33.6 |  | -0.2 |  | 1.1 |  |  |  | -2.3 |  | 3.6 |  | 3.6 |  | 3.6 |  | 3.6 |  | 3.6 |  | 0
2004-09-16 | -33.5 |  | -0.7 |  | 0.9 |  |  |  | -3.2 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 0.05
2004-09-17 | -33.5 |  | 0.6 |  | 1.3 |  |  |  | -0.9 |  | 3.8 |  | 3.8 |  | 3.8 |  | 3.8 |  | 3.8 |  | 0.63
2004-09-18 | -33.6 |  | 4.5 |  | 4.4 |  |  |  | 2.6 |  | 6.4 |  | 6.4 |  | 6.4 |  | 6.4 |  | 6.4 |  | 0
2004-09-19 | -33.5 |  | 2.3 |  | 2.6 |  |  |  | 0.5 |  | 6.3 |  | 6.3 |  | 6.3 |  | 6.3 |  | 6.3 |  | 0
2004-09-20 | -33.5 |  | 0.2 |  | 1.6 |  |  |  | -2.4 |  | 3.8 |  | 3.8 |  | 3.8 |  | 3.8 |  | 3.8 |  | 0
2004-09-21 | -33.3 |  | -0.8 |  | 1 |  |  |  | -4.7 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 0.01
2004-09-22 | -33.4 |  | -1.8 |  | 0.5 |  |  |  | -7.5 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 0.02
2004-09-23 | -32.8 |  | -4.7 |  | 0 |  |  |  | -10.6 |  | 2.9 |  | 2.9 |  | 2.9 |  | 2.9 |  | 2.9 |  | 0
2004-09-24 | -30.4 |  | -7.2 |  | -0.6 |  | -3.6 |  | -13.5 |  | 2.5 |  | 2.5 |  | 2.5 |  | 2.5 |  | 2.5 |  | 0
2004-09-25 | -30.1 |  | -8.6 |  | -1.3 |  | -4.8 |  | -15.7 |  | 1.7 |  | 1.7 |  | 1.7 |  | 1.7 |  | 1.7 |  | 0
2004-09-26 | -29.8 |  | -9.8 |  | -1.9 |  | -5.9 |  | -17.5 |  | 0.9 |  | 0.9 |  | 0.9 |  | 0.9 |  | 0.9 |  | 0.01
2004-09-27 | -29.2 |  | -10.8 |  | -2.2 |  | -6.9 |  | -18.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1.94
2004-09-28 | -29.2 |  | 4.5 |  | 4.5 |  | 3.2 |  | 3 |  | 4.8 |  | 4.8 |  | 4.8 |  | 4.8 |  | 4.8 |  | 0.91
2004-09-29 | -28.6 |  | 4.4 |  | 4.5 |  | 3.5 |  | 4.4 |  | 4.5 |  | 4.5 |  | 4.5 |  | 4.5 |  | 4.5 |  | 0.01
2004-09-30 | -6.7 |  | 4.3 |  | 4.4 |  | 3 |  | 2.6 |  | 4.7 |  | 4.7 |  | 4.7 |  | 4.7 |  | 4.7 |  | 0.01
2004-10-01 | -14.2 |  | 2.6 |  | 2.7 |  | 1.6 |  | 2.2 |  | 4.7 |  | 4.7 |  | 4.7 |  | 4.7 |  | 4.7 |  | 0
2004-10-02 | -16.8 |  | 2.1 |  | 2.1 |  | 1.2 |  | 1.4 |  | 4.3 |  | 4.3 |  | 4.3 |  | 4.3 |  | 4.3 |  | 0.29
2004-10-03 | -18.9 |  | 3.1 |  | 2.4 |  | 1.7 |  | 2.7 |  | 4.6 |  | 4.6 |  | 4.6 |  | 4.6 |  | 4.6 |  | 0.24
2004-10-04 | -19.7 |  | 5.2 |  | 5 |  | 1.8 |  | 2.8 |  | 6.3 |  | 6.3 |  | 6.3 |  | 6.3 |  | 6.3 |  | 0.02
2004-10-05 | -21.7 |  | 5.7 |  | 5.7 |  | 5.5 |  | 2 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 0
2004-10-06 | -22.2 |  | 2.6 |  | 2.6 |  | 1.9 |  | 0.6 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 0.01
2004-10-07 | -22.7 |  | 1.9 |  | 2.1 |  | 1.6 |  | -0.5 |  | 5.5 |  | 5.5 |  | 5.5 |  | 5.5 |  | 5.5 |  | 0.01
2004-10-08 | -15.1 |  | 1 |  | 1.7 |  | 1.1 |  | -2.1 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 0
2004-10-09 | 0.6 |  | 0.3 |  | 1.4 |  | 0.6 |  | -3.4 |  | 3.9 |  | 3.9 |  | 3.9 |  | 3.9 |  | 3.9 |  | 0.01
2004-10-10 | -4.8 |  | -0.3 |  | 1.2 |  | 0.1 |  | -4.6 |  | 3.8 |  | 3.8 |  | 3.8 |  | 3.8 |  | 3.8 |  | 0
2004-10-11 | -5.1 |  | -1.8 |  | 0.9 |  | -0.5 |  | -6.7 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 0
2004-10-12 | -5.4 |  | -5 |  | 0.5 |  | -1.3 |  | -8.7 |  | 3.2 |  | 3.2 |  | 3.2 |  | 3.2 |  | 3.2 |  | 0.01
2004-10-13 | -5 |  | -5.9 |  | 0.7 |  | -1.4 |  | -8.9 |  | 3.4 |  | 3.4 |  | 3.4 |  | 3.4 |  | 3.4 |  | 0.01
2004-10-14 | -4.2 |  | -7.1 |  | 0.1 |  | -2.4 |  | -10.9 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 0
2004-10-15 | -4.2 |  | 1.4 |  | 2 |  | -0.1 |  | -3.4 |  | 3.8 |  | 3.8 |  | 3.8 |  | 3.8 |  | 3.8 |  | 0.26
2004-10-16 | -4.2 |  | -4.4 |  | 0.5 |  | -1.5 |  | -6.5 |  | 3.3 |  | 3.3 |  | 3.3 |  | 3.3 |  | 3.3 |  | 0
2004-10-17 | -3.4 |  | -7.3 |  | -0.3 |  | -2.9 |  | -10.5 |  | 2.7 |  | 2.7 |  | 2.7 |  | 2.7 |  | 2.7 |  | 0
2004-10-18 | -3.5 |  | -8.6 |  | -0.6 |  | -4 |  | -13 |  | 2.3 |  | 2.3 |  | 2.3 |  | 2.3 |  | 2.3 |  | 0.01
2004-10-19 | -4.1 |  | -9.6 |  | -0.7 |  | -4.5 |  | -13.8 |  | 2.2 |  | 2.2 |  | 2.2 |  | 2.2 |  | 2.2 |  | 0
2004-10-20 | -4.6 |  | -10.3 |  | -0.8 |  | -5.2 |  | -14.9 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 0
2004-10-21 | -6.2 |  | -11.1 |  | -1.3 |  | -6.1 |  | -16.2 |  | 1.5 |  | 1.5 |  | 1.5 |  | 1.5 |  | 1.5 |  | 0
2004-10-22 | -8.6 |  | -12.2 |  | -1.5 |  | -7 |  | -17.4 |  | 1.1 |  | 1.1 |  | 1.1 |  | 1.1 |  | 1.1 |  | 0
2004-10-23 | -12.8 |  | -13.3 |  | -2.2 |  | -8.2 |  | -18.5 |  | 0.1 |  | 0.1 |  | 0.1 |  | 0.1 |  | 0.1 |  | 0
2004-10-24 | -13.8 |  | -14 |  | -1.5 |  | -8.6 |  | -18.8 |  | 1.8 |  | 1.8 |  | 1.8 |  | 1.8 |  | 1.8 |  | 0.07
2004-10-25 | -12.2 |  | -14.7 |  | -1.7 |  | -7.9 |  | -18.8 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0.01
2004-10-26 | -14.8 |  | -15.8 |  | -2.7 |  | -9.3 |  | -19.7 |  | -0.2 |  | -0.2 |  | -0.2 |  | -0.2 |  | -0.2 |  | 0.01
2004-10-27 | -14.9 |  | -16.8 |  | -3 |  | -10 |  | -20.2 |  | -0.5 |  | -0.5 |  | -0.5 |  | -0.5 |  | -0.5 |  | 0.02
2004-10-28 | -13.1 |  | -3.1 |  | 2 |  | -1.8 |  | -10.8 |  | 3.4 |  | 3.4 |  | 3.4 |  | 3.4 |  | 3.4 |  | 0.34
2004-10-29 | -14 |  | -5.6 |  | 0.3 |  | -3.3 |  | -6 |  | 3.2 |  | 3.2 |  | 3.2 |  | 3.2 |  | 3.2 |  | 0
2004-10-30 | -14.4 |  | -6.4 |  | 0.1 |  | -3.8 |  | -7.1 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 0
2004-10-31 | -15.1 |  | -7.6 |  | -0.6 |  | -4.9 |  | -9.4 |  | 2.6 |  | 2.6 |  | 2.6 |  | 2.6 |  | 2.6 |  | 0
2004-11-01 | -15.8 |  | -8.9 |  | -1.2 |  | -6.2 |  | -12.2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 0
2004-11-02 | -16.8 |  | -10.2 |  | -1.9 |  | -7.5 |  | -14 |  | 1.4 |  | 1.4 |  | 1.4 |  | 1.4 |  | 1.4 |  | 0.01
2004-11-03 |  |  | -10.9 |  | -2 |  | -8 |  | -14.9 |  | 1.4 |  | 1.4 |  | 1.4 |  | 1.4 |  | 1.4 |  | 0.02
2004-11-04 |  |  | -11.6 |  | -0.9 |  | -6.9 |  | -15.5 |  | 2.2 |  | 2.2 |  | 2.2 |  | 2.2 |  | 2.2 |  | 0.29
2004-11-05 |  |  | -5.3 |  | 0.1 |  | -3.4 |  | -6.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 0
2004-11-06 |  |  | -7.6 |  | -1 |  | -5.2 |  | -9.5 |  | 2.3 |  | 2.3 |  | 2.3 |  | 2.3 |  | 2.3 |  | 0.01
2004-11-07 |  |  | -9.4 |  | -1.8 |  | -6.5 |  | -11.8 |  | 1.5 |  | 1.5 |  | 1.5 |  | 1.5 |  | 1.5 |  | 0
2004-11-08 |  |  | -11.2 |  | -2.6 |  | -8 |  | -14.1 |  | 0.7 |  | 0.7 |  | 0.7 |  | 0.7 |  | 0.7 |  | 0
2004-11-09 |  |  | -13.8 |  | -4.3 |  | -10 |  | -17.1 |  | -1.2 |  | -1.2 |  | -1.2 |  | -1.2 |  | -1.2 |  | 0
2004-11-10 |  |  | -16.2 |  | -5.3 |  | -11.5 |  | -18.7 |  | -3.1 |  | -3.1 |  | -3.1 |  | -3.1 |  | -3.1 |  | 0
2004-11-11 |  |  | -17.8 |  | -5.8 |  | -12.5 |  | -19.2 |  | -3.8 |  | -3.8 |  | -3.8 |  | -3.8 |  | -3.8 |  | 0.01
2004-11-12 |  |  | -18.2 |  | -5.4 |  | -13 |  | -18.9 |  | -2.7 |  | -2.7 |  | -2.7 |  | -2.7 |  | -2.7 |  | 0.31
2004-11-13 |  |  | -7.5 |  | -0.8 |  | -5.1 |  | -8.1 |  | 2.3 |  | 2.3 |  | 2.3 |  | 2.3 |  | 2.3 |  | 0
2004-11-14 |  |  | -11.6 |  | -2.3 |  | -7.4 |  | -12 |  | 0.7 |  | 0.7 |  | 0.7 |  | 0.7 |  | 0.7 |  | 0.01
2004-11-15 |  |  | -14.9 |  | -3.4 |  | -9 |  | -14 |  | -0.9 |  | -0.9 |  | -0.9 |  | -0.9 |  | -0.9 |  | 0
2004-11-16 |  |  | -16.5 |  | -3.9 |  | -10.1 |  | -15 |  | -1.7 |  | -1.7 |  | -1.7 |  | -1.7 |  | -1.7 |  | 0.01
2004-11-17 |  |  | -17.4 |  | -4.2 |  | -10.9 |  | -15.9 |  | -2.1 |  | -2.1 |  | -2.1 |  | -2.1 |  | -2.1 |  | 0
2004-11-18 |  |  | -18.3 |  | -4.6 |  | -11.7 |  | -16.7 |  | -2.6 |  | -2.6 |  | -2.6 |  | -2.6 |  | -2.6 |  | 0
2004-11-19 |  |  | -19 |  | -4.7 |  | -12.2 |  | -17.1 |  | -2.7 |  | -2.7 |  | -2.7 |  | -2.7 |  | -2.7 |  | 0
2004-11-20 |  |  | -19.3 |  | -4.9 |  | -12.9 |  | -17.7 |  | -3.3 |  | -3.3 |  | -3.3 |  | -3.3 |  | -3.3 |  | 0.01
2004-11-21 |  |  | -19.7 |  | -5.4 |  | -13.8 |  | -18.6 |  | -4 |  | -4 |  | -4 |  | -4 |  | -4 |  | 0.04
2004-11-22 |  |  | -19.8 |  | -5.4 |  | -13.9 |  | -19 |  | -3.2 |  | -3.2 |  | -3.2 |  | -3.2 |  | -3.2 |  | 0.07
2004-11-23 |  |  | -2 |  | 0.3 |  | -3.1 |  | -10.8 |  | 2.7 |  | 2.7 |  | 2.7 |  | 2.7 |  | 2.7 |  | 0.37
2004-11-24 |  |  | 0.3 |  | 1.4 |  | -1.3 |  | 0.5 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 0.16
2004-11-25 |  |  | -2 |  | 0.7 |  | -1.5 |  | 0.6 |  | 3.4 |  | 3.4 |  | 3.4 |  | 3.4 |  | 3.4 |  | 0
2004-11-26 |  |  | -5.4 |  | -0.7 |  | -3.7 |  | -2.8 |  | 2.5 |  | 2.5 |  | 2.5 |  | 2.5 |  | 2.5 |  | 0
2004-11-27 |  |  | 2.3 |  | -1.5 |  | -4.9 |  | -4.2 |  | 1.7 |  | 1.7 |  | 1.7 |  | 1.7 |  | 1.7 |  | 0.25
2004-11-28 |  |  | -0.7 |  | 0.8 |  | -0.9 |  | 1.2 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 3.1 |  | 0
2004-11-29 |  |  |  |  | -0.1 |  | -2.2 |  | -0.6 |  | 2.7 |  | 2.7 |  | 2.7 |  | 2.7 |  | 2.7
2004-11-30
2004-12-01
2004-12-02
2004-12-03
2004-12-04
2004-12-05
2004-12-06
2004-12-07
2004-12-08
2004-12-09
2004-12-10
2004-12-11
2004-12-12
2004-12-13
2004-12-14
2004-12-15
2004-12-16
2004-12-17
2004-12-18
2004-12-19
2004-12-20
2004-12-21
2004-12-22
2004-12-23
2004-12-24
2004-12-25
2004-12-26
2004-12-27
2004-12-28
2004-12-29
2004-12-30
2004-12-31
Formulas:
Gauge Type: = [Gauge Type:, row above]+1
This exhibit represents the the raw submission format needed for groundwater and precipitation data . It is essential to the automation EEP needs for centralized storage of these data . The presence, location , and specific wording ,of the items in red are particularly critical pieces off information and/or critical to data automation needs.
Q = Data qualifier E = Known error; I = Known Impoundment
S = Instrument Status A = Absent; M = Malfunction; R = Replaced
Offset needs to be specifed. No correction = 0
Depth values listed will be corrected values
Precipition Source: Site Gauge; USGS Surrogate; Other Weather Station (Indicate Source)
This exhibit represents the the raw submission format needed for groundwater and precipitation data . It is essential to the automation EEP needs for centralized storage of these data . The presence, location , and specific wording ,of the items in red are particularly critical pieces off information and/or critical to data automation needs.
Q = Data qualifier E = Known error; I = Known Impoundment
S = Instrument Status A = Absent; M = Malfunction; R = Replaced
Offset needs to be specifed. No correction = 0
Depth values listed will be corrected values
Precipition Source: Site Gauge; USGS Surrogate; Other Weather Station (Indicate Source)
Note on W12: Michael T. Lee: Site Gauge; USGS Surrogate; Other Weather Station (Indicate Source)
Note on L125: NCDOT: 8e531b2 replaced with 9796B95 pm 4/20/2004
Note on N125: NCDOT: 8e531b2 replaced with 9796B95 pm 4/20/2004
Note on P125: NCDOT: 8e531b2 replaced with 9796B95 pm 4/20/2004
Note on R125: NCDOT: 8e531b2 replaced with 9796B95 pm 4/20/2004
Note on T125: NCDOT: 8e531b2 replaced with 9796B95 pm 4/20/2004
Note on H236: NCDOT: 8E53A81 would not download
Note on D280: NCDOT: has been under water, buried by debree
Note on H280: NCDOT: 8E53A81 replaced by 97955CD on 9/23/2004
Note on L280: NCDOT: Has been underwater, buried by debree
Note on N280: NCDOT: Has been underwater, buried by debree
Note on P280: NCDOT: Has been underwater, buried by debree
Note on R280: NCDOT: Has been underwater, buried by debree
Note on T280: NCDOT: Has been underwater, buried by debree